## Status Update
RPM Facilitation
Status Report
Updated September 28, 2011
RPM Topic | Charge Issue or Address Tariff Requirement | Provide Education | Document Interests | Develop Design Components | Develop Solution Options | Reduce Solution Options | Package Solutions | Reduce Packages | Build Consensus | Vote at MRC/MC | Inform Board | File with FERC
Triennial Review Track
All Items | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 10/12/11 for MRC 10/20/11 for MC | Due before 10/31/11 | 2011-11-30
MRC Track
New Entry Pricing Adjustment | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Will send polls afternoon of 10/3/11. Due back to burdit@pjm.com by 4 pm 10/5/11 |  | 11/16/11 for MRC 11/22/11 for MC |  | 2011-11-30
Minimum Offer Price Rule Exception Process | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Fixed Resource Requirement Alternative | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Self Supply | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Energy and Ancillary Service Offset | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Performance Assessment Track
CETL | Complete | Complete | PJM will provide initial matrix draft - stakeholders will work the matrix on 10/7/11 | [6 empty] | 11/16/11 for MRC 11/22/11 for MC |  | 2011-11-30
Load Forecast | Complete | Complete
Voluntary, Long-term Auction | Complete | Complete
2.5% Holdback | Complete | Complete
Triennial Review Track
Tariff Attachment DD, Section 5.10 (a) - requires Board to file recommended changes to VRR curve, CONE and EAS offset by 12/1/11.
MRC Charge Track
Proposed changes regarding this item will be filed by 11/30/11 to allow inclusion in the next BRA.
Performance Assessment Track
Tariff Attachment DD, Section 17.6 - requires performance assessment to be filed by 11/30/11.
Proposed changes regarding items included in the short-term charge approved by the MRC on 915/11 will be filed by 11/30/11 to allow inclusion in the next BRA.