## Meeting Content (hidden)
Capacity Senior Task Force Meeting Content
Meeting
| 1 | 2 | 3 | 4 | 5 | 6
| 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon
Topic(s) | 2012-04-12 | 2012-04-19 | 2012-04-27 | 2012-05-04 | 2012-05-22 | 2012-06-06 | 2012-06-28 | 2012-07-26 | 2012-08-01
Admin | bar: 2012-04-12
Charter | bar: 2012-04-12 to 2012-04-19
Work Plan | bar: 2012-04-12
Provide Education | bar: 2012-04-12
Document Interests | bar: 2012-04-19
Develop Design Components | bar: 2012-04-19 to 2012-04-27
Develop Solution Options | bar: 2012-04-27 to 2012-05-04
Reduce Solution Options | bar: 2012-05-04
Package Solutions | bar: 2012-05-04 to 2012-05-22
Reduce Package Options | bar: 2012-05-22 to 2012-06-06
Build Concensus | bar: 2012-06-06
Vote at MRC/MC | 2012-06-28: First Read; 2012-07-26: X
File with FERC | bar: 2012-08-01

## With dates (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProvide Education
Proposal Development |  |  | 13 |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
Problem Investigation |  |  |  | 20
Proposal Development |  |  |  |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
Demand Response Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | Mar. 2013
üProvide Education
Document Interests |  |  |  | 20
Develop & Refine Design Components | [5 empty] | 14
Develop & Refine Solution Options | [6 empty] | 5
Develop & Refine Solution Packages
Build Consensus
First Read @ MRC
Vote at MRC/MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
Refine Interests |  |  | 13
Refine Design Components
Develop & Refine Solution Options |  |  |  |  | 2012-10-01: 11; 2012-11-01: 14
Develop & Refine Solution Packages |  |  |  |  | 2012-12-01: 5
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC/MC | bar: 2013-04-01
FERC Filing |  |  |  |  | 2013-05-01: 2012-05-31

## 2012- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
Proposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
üRefine Interests
üRefine Design Components
Develop & Refine Component Options | bar: 2012-10-01 to 2012-11-01
Develop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC | bar: 2013-04-01
Vote at MC | bar: 2013-05-01
FERC Filing |  |  |  | 2013-05-01: 2012-05-31

## 2013- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
|  |  | 2012 |  |  |  | 2013
2012 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
üProvide Education
Document Interests | bar: Oct
Develop & Refine Design Components | bar: Nov
Develop & Refine Component Options | bar: Dec to 2013 Jan
Develop & Refine Solution Packages | bar: 2013 Feb to 2013 Mar
Build Consensus | bar: 2013 Mar to 2013 Apr
First Read @ MRC | bar: 2013 Apr
Vote at MRC | bar: 2013 May
Vote at MC | bar: 2013 Jun
|  |  | 2012 | 2013 Jan: 2013
2013 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Provide Education | bar: 2013 Jan
Document Interests | bar: 2013 Feb
Develop & Refine Design Components | bar: 2013 Feb to 2013 Mar
Develop & Refine Component Options | bar: 2013 Apr to 2013 May
Develop & Refine Solution Packages | bar: 2013 Jun
Build Consensus | bar: 2013 Jul to 2013 Aug
First Read @ MRC | bar: 2013 Sep
Vote at MRC | bar: 2013 Oct
Vote at MC | bar: 2013 Nov

## CW 7-14 (hidden)
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Cold Weather Resource Performance Improvement | Providing Education & Identifying Interests Design Component Development | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Gas Unit Commitment Coordination | May MRC approved problem statement Providing Education, Identifying Interests, and Prioritizing Issue topics | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | MRC Endorsement of the Spinning and Primary Reserve Requirements MRC Endorsement received; short-term proposal implemented | Short term solution implemented June 1 through September 30; Long term solution to be filed with FERC by November 1, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Proposal approved is to increase day-ahead and real-time reserve requirements under specified conditions by a fixed reserve adder when additional resources are scheduled to cover operational uncertainty | Problem Statement | Issue Charge
Energy Market Uplift | Composing solution options and packages for cost allocation. PJM to propose a solution in late June.PJM presented a package with several solutions options at the 6/19 EMUSTF. Continued discussions on solution options. | April 1 2015 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Generation Capacity Resource Performance | New (expected to go the June MRC for first read of problem statement)First read on 6/26 and planned for approval at the 7/31 MRC | TBD | TBD | Review the penalties for non-performance and incentives for performance during peak days and / or days when emergency procedures are issued for capacity emergencies
Unit Characteristics | Completed internal review of the information provided by Generation Owners as part of Fall 2013 generator survey is underway. Continued outreach with GOs to improve information sharing; Consideration of business rules and/or internal processes to enhance consistent and timely assessment of generator information. | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. Voting is complete. There was no consensus. Standard development is underway. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Unit Market Offers | Problem statement to be developed. Problem statement to be reviewed at 7/9 MIC | TBD | MIC | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Offer Caps | Developing component solution options and beginning to package solutions. | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Data Sharing with Gas Industry | Internal PJM effort that is in progress. | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Waivers | Changes made to M-13 to clarify existing rules for granting waivers. Additional processes under development. COMPLETE Implemented 6/1 with the new version of M-13 | November-14 June- 14 | OC | Confirm mechanism by which resources seek waivers for fuel emission limitations and better understand conditions under which relief may be granted | PJM Manual 13
Interregional Coordination | COMPLETE: -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC IN PROGRESS: - Mutual emergency procedure language in the VACAR/PJM RC Agreement in review - EMS display with Dominion units used to meet VACAR reserve obligations and reserve position in progress | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
Voltage Reduction Emergency Procedure | Survey distributed to Transmission Owners and responses being presented back to stakeholders. Data being finalized.Survey responses from TOs utilized to create Voltage reduction plans. Plans added to the Dispatcher SharePoint site and will be added to M13 | 2014-10-01 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
Regulation Market Rules | Problem statement to be developed.First read of the problem statement planned for 8/6 MIC | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
External Capacity | New Tool has been developed and is in the testing phase | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Communications & Procedures | PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alerts. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Public Appeals | Internal analysis has started to quantify the impact.Draft changes to the Public appeals are in review and will be distributed to the SOS-T | 2014-10-01 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated July 3, 2014

## CW 8-14 (hidden)
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Cold Weather Resource Performance Improvement | Providing Education & Design Component and Solution Option Development | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Gas Unit Commitment Coordination | May MRC approved problem statement Providing Education and Design Matrix Development for the communication issue Identifying Interests, and Prioritizing Issue topics | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | MRC Endorsement of the Spinning and Primary Reserve Requirements MRC Endorsement received; short-term proposal implemented. Long-term solutions are currently being developed for both pieces of the issue charge: energy & reserve pricing and interchange volatility | Short term solution implemented June 1 through September 30; Long term solution to be filed with FERC by November 1, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Proposal approved is to increase day-ahead and real-time reserve requirements under specified conditions by a fixed reserve adder when additional resources are scheduled to cover operational uncertainty Determine whether enhancements can be made to existing rules for transaction scheduling to improve system and price stability | Problem Statement | Issue Charge
Energy Market Uplift | Composing solution options and packages for cost allocation. PJM to propose a solution in late June.PJM presented a package with several solutions options at the 6/19 EMUSTF. Continued discussions on solution options. | April 1 2015 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Generation Capacity Resource Performance | New (expected to go the June MRC for first read of problem statement)First read on 6/26 and planned for approval at the 7/31 MRC- introduced as the High Availability Capacity Problem Statement | TBD | TBD | Review the penalties for non-performance and incentives for performance during peak days and / or days when emergency procedures are issued for capacity emergencies
Unit Characteristics | Completed internal review of the information provided by Generation Owners as part of Fall 2013 generator survey is underway. Continued outreach with GOs to improve information sharing; Consideration of business rules and/or internal processes to enhance consistent and timely assessment of generator information. | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. Voting is complete. There was no consensus. Standard development is underway. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Unit Market Offers | Problem statement to be reviewed at 7/9 MIC Problem statement was endorsed at 7/9 MIC. Issue charge will be reviewed at 8/6 MIC | TBD 2014-2015 Winter | MIC | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Offer Caps | Developing component solution options and beginning to package solutions. | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Data Sharing with Gas Industry | Internal PJM effort that is in progress. Specifically - 1) improve internal FERC 787 data sharing process; 2) development of a template, in collaboration with other ISO/RTOs, to facilitate sharing of electric industry operational information and gas pipeline information between the two industries; and an internal dashboard of electrical interconnection areas impacted by pipeline issues. | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Interregional Coordination | COMPLETE: -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC IN PROGRESS: - Mutual emergency procedure language in the VACAR/PJM RC Agreement in review - EMS display with Dominion units used to meet VACAR reserve obligations and reserve position in progress | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
Voltage Reduction Emergency Procedure | Survey distributed to Transmission Owners and responses being presented back to stakeholders. Data being finalized. Survey responses from TOs utilized to create Voltage reduction plans. Plans added to the Dispatcher SharePoint site and will be added to M13 | 2014-10-01 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
Regulation Market Rules | Problem statement to be developed. First read of the problem statement planned for 8/6 MIC | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
External Capacity | New Tool has been developed and is in the testing phase | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Communications & Procedures | PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alerts. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Public Appeals | Internal analysis has started to quantify the impact. Draft changes to the Public appeals are in review and will be distributed to the SOS-. Public appeal M-13 language changes are being discussed as part of the SOS-T on 7/30. Internal discussion in progress to determine the impact of Public Appeals on RTO load | 2014-10-01 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
Winter Outage Rate and Reserve planning studies | Internal analysis has started to quantify the impact of higher forced outage rates on future IRM requirements | TBD | Planning Committee | This work consists of the following items: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 -Analysis of the 2018/19 Delivery Year to develop possible recommendations regarding changes to the RPM BRA to recognize weather-related winter risk - Analysis of the RTEP year of 2019/20 to develop winter CETOs and CETLs based on a series of gas outage scenarios. - Evaluation of further scenarios in which greater levels of natural gas will be used to generate electricity and what potential operational issues this could cause, as well as what electric infrastructure will be needed to maintain reliability. | Presentation- Assessment of Winter LOLE Risk at the RTO Level Presentation- Winter Generation Outage Analysis
Gas Infrastructure Future Adequacy | Target 1- Baseline systems draft report has been posted | Study results by 2014 | PC | EIPC Gas-Electric System Interface Study includes four Targets: 1. Baseline systems (posted) 2. Infrastructure capability (October) 3. Contingency analysis (December) 4. Dual-Fuel evaluation (November)
Waivers | COMPLETE Implemented 6/1 with the new version of M-13 to clarify that PJM does not grant environmental waivers but will work with the GO if requested/notified of limitations. | November-14 June- 14 | OC | Confirm mechanism by which Generation Owners work with PJM during resources seek waivers for fuel emission limitations and better understand conditions under which relief may be granted. | PJM Manual 13
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated August 4, 2014

## HW 8-14 (hidden)
Hot Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials | Hot Weather Report Recommendation Mapping ID
System Modeling | COMPLETE: Updated PJM's model & telemetry in the impacted areas. IN PROGRESS: Draft documentation on the practices and processes is currently under review. | 2014-12-31 | MC Webinar / Data Management Subcommittee / OC | Improve the PJM model and telemetry in the areas where issues were experienced during the events of September 9 - 11, as needed. 'Update PJM's modeling processes and practices to include PJM's expectations of Transmissions Owners' input; as well the approach to implementing modelling and telemetry across the transmission and sub-transmission system. |  | 1, 2
Facility Limits | External Complete for MISO, NYISO in progress, need to continue work with other neighbors Internal proposal going to SOS-T end of August | 2014-12-18 | SOS-T | Review Facility limits with neighboring companies for pre- and post- contingency information. |  | 4
Synchronized Reserves | Code changes for Tier 1 Reserve calculations are scheduled to be included in the next Alstom release (target July 2014) Instantaneous Reserve Check change is scheduled for 2015 project | 2015-09-30 | OC / Member Dispatcher Training | Review and modify Tier 1 reserve calculations to more accurately reflect the available reserves from synchronized generating units Review the current Instantaneous Reserve Check (IRC) mechanism for improvements; and identify methods for improving the quality of data being reported by GOs, including reinforcement through training. Improve current methods of providing PJM dispatchers with an accurate presentation of the available reserves on the system at any given time both at an aggregate level and unit-specific. |  | 10, 11, 12, 20
Demand Response | COMPLETE: Demand Response filing submitted and approved by the FERC in May 2014 MRC approved Manual 11, 13, and 18 changes for June 1 and dispatcher member training have been completed IN PROGRESS: Demand Response sub zonal creation in progress. Development in progress for a tool to visualize the location and MW of relief of DR | 2014-09-30 | PJM Internal | Improve DR operational flexibility to include shorter lead time, sub zonal calls, calls outside of emergencies, and shorter minimum run times. Improve Demand Response reliability by defining more subzones proactively and mapping Demand Response Resources to nearest substation. Improve Dispatcher's visibility of location and MW relief from Demand Response |  | 10, 13,14, 15
PJM Cascading Outage Analysis Procedure | A tool to automate trending for potential cascading contingencies is under development. | 2014-12-15 | SOS / OC | Review PJM's Cascading Outage Analysis procedure and determine how it can be improved as well as automated. |  | 6
Behind the Meter Generation | Internal PJM discussions to begin in August 2014. | 2015-03-15 | OC | Establish and document PJM's approach for representing known Behind the Meter generation and the related operating criteria for Dispatchers. This effort will require coordination with the TOs and the States. |  | 7
Emergency Procedures Tool | COMPLETE: Logging for load shed events and training complete. Training also complete for contingency management. Contact information and communication policies updates have been completed IN PROGRESS: Filtering capabilities by County/State for substations in the electronic notification tool will be included in upcoming enhancement project | 2015-05-15 | OC | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the proper logging of these events in the application, training for PJM Dispatchers, and ensuring the proper contacts are included in the tool. Also, look for improvements to Emergency Procedures to allow for advanced filtering by state, message type, etc. |  | 8, 17
Unit Characteristics | This overlaps with the cold weather recommendation for Unit Characteristics. COMPLETE: Sorting functionality in the Dispatcher Management Tool has been completed IN PROGRESS: Completed internal review of the information provided by Generation Owners as part of Fall 2013 generator survey is underway. Continued outreach with GOs to improve information sharing. Mapping for validating generator performance is in progress. | 2014/2015 | OC | Develop and implement a process for validating generator performance data (ecomax, emergency max, spin max, etc.) and improving tools for Dispatchers to view unit availability. |  | 20, 21
Communication and Notification Protocols | Training completed for PJM and Member Dispatchers on M1 directive language | 2015-05-15 | OC / Member Dispatcher Training | Enhance tools, documentation, and training to improve communication and notification processes during crises: -Document PJM crisis communication policies -Manual 1 directive language with the PJM and TO Dispatchers |  | 5, 8, 16, 17
PJM EMS Non-Converge and Contingency Management Tools and Processes | Reinforcement training for operators on contingency management and non-converge situations completed | 2014-12-21 | OC / MC Webinar | Review PJM EMS non-converge procedures and EMS tools to present non-converge situations to PJM operators to include troubleshooting processes. Also look for improvements in the EMS to help manage constraints. |  | 9,22
Load Forecasting | COMPLETE: Hot and Cold Weather alert process training and manual updates have been completed | 2014-12-15 | OC | Review the current process of handling notification of load forecast errors as well as improving Dispatcher processes for modifying the load forecast when load forecast errors are identified and hot and cold weather alerts considered. 'Review the processes for conducting weather and load forecasting, with consideration for sampling and weighting of weather data throughout the RTO footprint; and methods of developing load forecasts on a sub zonal basis. |  | 18, 19
Operation Guide (Pigeon River) | COMPLETE Operation Guide has been updated and reviewed with the impacted parties and posted to the PJM Internal Dispatcher website. | 2014-02-28 | PJM Internal | Update the Operation guide with relay limits and pre-contingency load shed procedures for Pigeon River. |  | 3
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated August 4, 2014

## CW 9-14 (hidden)
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Cold Weather Resource Performance Improvement | Providing Education & Design Component and Solution Option Development | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Gas Unit Commitment Coordination | Design Matrix Development for the communication issue. Continued education and discussion/development of Solution Options for the high priority issues | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | MRC Endorsement of short-term proposal received; short-term proposal implemented. Long-term solutions are currently being developed for both pieces of the issue charge: energy & reserve pricing and interchange volatility | Short term solution implemented June 1 through September 30; Long term solutions to be voted on at October MIC/MRC and November MC, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Determine whether enhancements can be made to existing rules for transaction scheduling to improve system and price stability | Problem Statement | Issue Charge
Energy Market Uplift | PJM presented a package with several solutions options at the 6/19 EMUSTF. Continued discussions on solution options.The group continues to discuss methodologies for cost allocation with the target of voting on them in the Fall. PJM has put forward a new proposal that more closely mimics the current allocation methodology with minor changes. The original proposal was not supported by stakeholders and therefore will likely get dropped. | April 1 2015 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Generation Capacity Resource Performance Capacity Performance | Introduced as the Capacity Performance Problem Statement. Three meetings have been completed to review the Problem Statement and Whitepaper. The next meeting is scheduled for 9/11 | TBD | Enhanced Liaison Committee Process | The Problem Definition: Need to refine the definition of capacity •Fuel security – dependable fuel source •Performance incentives and penalties •Capacity resources must be highly available for operations •Require flexible unit operational parameters | Problem Statement | Capacity Performance Proposal
Unit Characteristics | Completed internal review of the information provided by Generation Owners as part of Fall 2013 generator survey is underway. Continued outreach with GOs to improve information sharing; Consideration of business rules and/or internal processes to enhance consistent and timely assessment of generator information. | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. Voting is complete. There was no consensus. Standard development is underway. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Unit Market Offers | Problem statement was endorsed at 7/9 MIC. Issue charge will be reviewed at 8/6 MICItems from this issue will be discussed with Capacity Performance | TBD 2014-2015 Winter | Enhanced Liaison Committee Process | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Offer Caps | Developing component solution options and beginning to package solutions. Vote completed for three packages. Package B received more than 50% approval (remove the offer cap on cost offer, but limit the 10% adders to $90 dollars above the previous offer cap of $1000). First read at the 8/21 MRC completed | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Data Sharing with Gas Industry | Internal PJM effort that is in progress will include: -Improvement of internal FERC 787 data sharing process -Development of a template, in collaboration with other ISO/RTOs, to facilitate sharing of electric industry operational information and gas pipeline information between the two industries (Draft template to discussed at the meeting with INGAA on 9/3) -Internal dashboard of electrical interconnection areas impacted by pipeline issues (v. 1.0 for this winter) | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Interregional Coordination | COMPLETE: -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC -Mutual emergency procedure language in the VACAR/PJM RC Agreement completed IN PROGRESS: - EMS display with Dominion units used to meet VACAR reserve obligations and reserve position in progress | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
Voltage Reduction Emergency Procedure | Survey distributed to Transmission Owners and responses being presented back to stakeholders. Data being finalized. Survey responses from TOs utilized to create Voltage reduction plans. Voltage reduction plans have been added to the Dispatcher SharePoint site and is planned to be added to M13 by 10/14 | 2014-10-01 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
Regulation Market Rules | First read of the problem statement planned for 8/6 MIC The problem statement was presented at the 8/26 MIC. The committee discussed the problem statement and requested that PJM come back with more information and a more concise problem statement. | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
External Capacity | New Tool has been developed and is in the testing phase | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Public Appeals | Public appeal M-13 language changes are being discussed as part of the SOS-T on 7/30. COMPLETE: Internal discussions completed to determine the impact of Public Appeals on RTO load: At this time there is no accurate method utilized in the industry to determine the impact. IN PRORESS: Draft updates to M-13 in progress. | 2014-10-01 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
Winter Outage Rate and Reserve planning studies | Internal analysis has started to quantify the impact of higher forced outage rates on future IRM requirements COMPLETE: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 was completed and reviewed at the PC and Capacity Performance mtgs. -Gas outage scenarios development was completed IN PROGRESS: -CETO/CETL work is in progress -Evaluation of further scenarios and potential operational issues where natural gas will be used to generate electricity is in progress | TBD | Planning Committee | This work consists of the following items: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 -Analysis of the 2018/19 Delivery Year to develop possible recommendations regarding changes to the RPM BRA to recognize weather-related winter risk - Analysis of the RTEP year of 2019/20 to develop winter CETOs and CETLs based on a series of gas outage scenarios. - Evaluation of further scenarios in which greater levels of natural gas will be used to generate electricity and what potential operational issues this could cause, as well as what electric infrastructure will be needed to maintain reliability. | Presentation- Assessment of Winter LOLE Risk at the RTO Level Presentation- Winter Generation Outage Analysis
Gas Infrastructure Future Adequacy | Target 1- Baseline systems draft report has been posted Target 2 initial modeling runs to determine the adequacy of the pipeline infrastructure to meet electric system needs are scheduled to be delivered to Planning Authorities for review by 9/1 | Study results by 2014 | PC | EIPC Gas-Electric System Interface Study includes four Targets: 1. Baseline systems (posted) 2. Infrastructure capability (October) 3. Contingency analysis (December) 4. Dual-Fuel evaluation (November) | Presentation- EIPC Gas-Electric System Interface Study Update
Communications & Procedures | PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alerts. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Waivers | COMPLETE Implemented 6/1 with the new version of M-13 to clarify that PJM does not grant environmental waivers but will work with the GO if requested/notified of limitations. | November-14 June- 14 | OC | Confirm mechanism by which Generation Owners work with PJM during resources seek waivers for fuel emission limitations and better understand conditions under which relief may be granted. | PJM Manual 13
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated September 3, 2014

## HW 9-14 (hidden)
Hot Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials | Hot Weather Report Recommendation Mapping ID
PJM EMS Non-Converge Procedures and Tools | Creation of tools to investigate non-converge SA results is in progress | 2014-08-01 |  | Review PJM EMS non-converge procedures and EMS tools to present non-converge situations to PJM operators to include troubleshooting processes. |  | 9
Demand Response | Development in progress for a tool to visualize the location and MW of relief of DR | 2014-09-01 | PJM Internal | Develop tools to aid the dispatchers in visualization of the location and MW relief from DR |  | 15
Unit Characteristics | This overlaps with the cold weather recommendation for Unit Characteristics. See the Cold Weather Recommendation Matrix for status notes | 2014-12-01 | OC | Develop and implement a process for validating generator performance data (ecomax, emergency max, spin max, etc.) |  | 20
Emergency Procedures Tool | Filtering capabilities by County/State for substations in the electronic notification tool will be included in upcoming enhancement project | 2014-12-01 |  | Adding filtering capability to the electronic notification tool to allow PJM staff and stakeholders to determine the applicability of messages they receive. Work with SOS-T (or, capture from DIMA project) to acquire appropriate County/State level info for each Substation/Load in the EMS Model Conduct training for dispatch as needed |  | 17
Facility Limits | External review with MISO and NYISO is complete. Work with other facilities is still in progress Internal proposal going to SOS-T end of August. Load Dump Rating Methodology proposal reviewed at the 8/27 SOS-T. Additional work for Manual 3 update, TERM modifications, and Setting deadlines for initial submission of new ratings is in progress | 2014-12-01 | SOS-T | Review Facility limits with neighboring companies for pre- and post- contingency information. |  | 4
PJM Cascading Outage Analysis Procedure | A tool to automate trending for potential cascading contingencies is under development. | 2014-12-15 | SOS / OC | Review PJM's Cascading Outage Analysis procedure and determine how it can be improved as well as automated. |  | 6
System Modeling | Draft documentation on the practices and processes is currently under review. | 2014-12-31 | MC Webinar / Data Management Subcommittee / OC | Update PJM's modeling processes and practices to include PJM's expectations of Transmissions Owners' input; as well the approach to implementing modelling and telemetry across the transmission and sub-transmission system. |  | 1
Behind the Meter Generation | Internal PJM discussions to begin in August 2014. | 2015-03-15 | OC | Establish and document PJM's approach for representing known Behind the Meter generation and the related operating criteria for Dispatchers. This effort will require coordination with the TOs and the States. |  | 7
Synchronized Reserves | Internal meeting scheduled for Q4 2014 to review scope for Instantaneous Reserve Check (IRC) Tool refresh project | 2015-06-01 |  | Improve current methods of providing PJM dispatchers with an accurate presentation of the available reserves on the system at any given time both at an aggregate level and unit-specific. |  | 12
Synchronized Reserves | Instantaneous Reserve Check change is scheduled to be a 2015 Operations project. | 2015-09-01 |  | Review the current Instantaneous Reserve Check (IRC) mechanism for improvements; and identify methods for improving the quality of data being reported by GOs, including reinforcement through training. |  | 11
Synchronized Reserves | COMPLETE: 8/14 Tier 1 calculations are being utilized to reflect available reserves | 2014-07-01 | OC / Member Dispatcher Training | Review and modify Tier 1 reserve calculations to more accurately reflect the available reserves from synchronized generating units |  | 10
Communication and Notification Protocols | COMPLETED: 7/14 Training completed for PJM and Member Dispatchers on M1 directive language | 2015-05-15 | OC / Member Dispatcher Training | Enhance tools, documentation, and training to improve communication and notification processes during crises: -Document PJM crisis communication policies -Manual 1 directive language with the PJM and TO Dispatchers |  | 5, 8, 16
PJM EMS Non-Converge and Contingency Management Training | COMPLETE: 7/14 Reinforcement training for operators on contingency management and non-converge situations completed | 2014-07-01 | OC / MC Webinar | Provide reinforcement training for operators on contingency management (contingency trending, PCLLRW, load shed, etc.) in the control room simulator. This this training to look for EMS enhancements for managing constraints |  | 22
Unit Characteristics | COMPLETE: 7/14 This overlaps with the cold weather recommendation for Unit Characteristics. Sorting functionality in the Dispatcher Management Tool has been completed | 2014-04-01 | OC | Improve the generation sorting functionality in the Dispatcher Management Tool. Available and max emergency units should be included on the normal sort. Max Emergency units should be flagged for easy identification. |  | 21
Demand Response | COMPLETE: 7/14 PJM load management subzone information updated | 2014-07-01 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members, should define more subzones proactively across the PJM footprint. |  | 14(1)
Demand Response | COMPLETE: 7/14 DR mapping with zip codes completed | 2014-09-14 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members Map Demand Response Resources to nearest substation. |  | 14(2)
System Modeling | COMPLETE: 7/14 Updated PJM's model & telemetry in the impacted areas. | 2014-07-14 | MC Webinar / Data Management Subcommittee / OC | Improve the PJM model and telemetry in the areas where issues were experienced during the events of September 9 - 11, as needed. |  | 2
Emergency Procedures Tool | COMPLETE: 6/14 Manual 13 revisions are completed | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (1) Develop process language for logging local shed events |  | 8(1)
Emergency Procedures Tool | COMPLETE: 6/14 Training completed in Cycle 4 training | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (2) Develop training to reinforce process and tools |  | 8(2)
Emergency Procedures Tool | COMPLETE: 6/14 Contact list reviewed and training has been completed | 2014-04-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (3) Ensure contact lists are updated and stakeholder are enrolled properly |  | 8(3)
Demand Response | COMPLETE: 5/14 Demand Response filing submitted and approved by the FERC in May 2014 MRC approved Manual 11, 13, and 18 changes for June 1 and dispatcher member training have been completed | 2014-05-01 |  | Implement through the stakeholder process to improve Demand Response operational flexibility to include shorter lead time; sub zonal calls, calls outside of emergencies, and shorter minimum run times. |  | 13
Load Forecasting | COMPLETE: 4/14 Hot and Cold Weather alert process training and manual updates have been completed | 2014-12-15 | OC | Review the current process of handling notification of load forecast errors as well as improving Dispatcher processes for modifying the load forecast when load forecast errors are identified and hot and cold weather alerts considered. 'Review the processes for conducting weather and load forecasting, with consideration for sampling and weighting of weather data throughout the RTO footprint; and methods of developing load forecasts on a sub zonal basis. |  | 18, 19
Operation Guide (Pigeon River) | COMPLETE: 3/14 Operation Guide has been updated and reviewed with the impacted parties and posted to the PJM Internal Dispatcher website. | 2014-02-28 | PJM Internal | Update the Operation guide with relay limits and pre-contingency load shed procedures for Pigeon River. |  | 3
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated September 3, 2014

## CW 10-14 (hidden)
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Cold Weather Resource Performance Improvement | Solution Option Development First read of the solution package including manual language changes completed at the OC and MRC. Endorsement to be requested at the October OC and MRC. | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Gas Unit Commitment Coordination | Continued education and discussion/development of Solution Options for the high priority issues Review of 2014/2015 Winter Scope Solution Options is in progress | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | MRC Endorsement of short-term proposal received; short-term proposal implemented. Long-term solutions are currently being developed for both pieces of the issue charge: energy & reserve pricing and interchange volatility | Short term solution implemented June 1 through September 30; Long term solutions to be voted on at October MIC/MRC and November MC, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Determine whether enhancements can be made to existing rules for transaction scheduling to improve system and price stability | Problem Statement | Issue Charge
Energy Market Uplift | The group continues to discuss methodologies for cost allocation with the target of voting on them in the Fall. PJM has put forward a new proposal that more closely mimics the current allocation methodology with minor changes. The original proposal was not supported by stakeholders and therefore will likely get dropped. | April 1 2015 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Generation Capacity Resource Performance Capacity Performance | Comments from initial whitepaper have been posted. Updated whitepaper will be posted on 10/7. | TBD | Enhanced Liaison Committee Process | The Problem Definition: Need to refine the definition of capacity •Fuel security – dependable fuel source •Performance incentives and penalties •Capacity resources must be highly available for operations •Require flexible unit operational parameters | Problem Statement | Capacity Performance Proposal
Unit Characteristics | Completed internal review of the information provided by Generation Owners as part of Fall 2013 generator survey is underway. Continued outreach with GOs to improve information sharing; Consideration of business rules and/or internal processes to enhance consistent and timely assessment of generator information. Survey will be sent out in October. | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. Voting is complete. There was no consensus. Standard development is underway. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Unit Market Offers | Items from this issue will be discussed with Capacity Performance | TBD 2014-2015 Winter | Enhanced Liaison Committee Process | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Offer Caps | Vote completed for three packages. Package B received more than 50% approval (remove the offer cap on cost offer, but limit the 10% adders to $90 dollars above the previous offer cap of $1000). First read at the 8/21 MRC completed All packages failed at the MRC. The group will meet again on 10/10. | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Data Sharing with Gas Industry | Internal PJM effort that is in progress will include: -Improvement of internal FERC 787 data sharing process -Development of a template, in collaboration with other ISO/RTOs, to facilitate sharing of electric industry operational information and gas pipeline information between the two industries (Draft template to discussed at the meeting with INGAA on 9/3) -Internal dashboard of electrical interconnection areas impacted by pipeline issues (v. 1.0 for this winter) | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Interregional Coordination | COMPLETE: -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC -Mutual emergency procedure language in the VACAR/PJM RC Agreement completed IN PROGRESS: - EMS display with Dominion units used to meet VACAR reserve obligations and reserve position in progress. The new EMS display for VACAR reserves will be available by 12/1/14. | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
Voltage Reduction Emergency Procedure | Survey distributed to Transmission Owners and responses being presented back to stakeholders. Data being finalized. Survey responses from TOs utilized to create Voltage reduction plans. Voltage reduction plans have been added to the Dispatcher SharePoint site and is planned to be added to M13 by 10/14 | 2014-10-01 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
Regulation Market Rules | The problem statement was presented at the 8/26 MIC. The committee discussed the problem statement and requested that PJM come back with more information and a more concise problem statement. PJM is in the process of drafting a whitepaper to provide clarification and reasoning on the Regulation Market Rules enhancement recommendations. | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
External Capacity | Tool has been developed and is in the testing phase | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Public Appeals | COMPLETE: Internal discussions completed to determine the impact of Public Appeals on RTO load: At this time there is no accurate method utilized in the industry to determine the impact. IN PRORESS: Draft updates to M-13 in progress. | 10/1/2014 1/1/15 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
Winter Outage Rate and Reserve planning studies | Internal analysis has started to quantify the impact of higher forced outage rates on future IRM requirements COMPLETE: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 was completed and reviewed at the PC and Capacity Performance mtgs. -Gas outage scenarios development was completed IN PROGRESS: -CETO/CETL work is in progress -Evaluation of further scenarios and potential operational issues where natural gas will be used to generate electricity is in progress | TBD | Planning Committee | This work consists of the following items: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 -Analysis of the 2018/19 Delivery Year to develop possible recommendations regarding changes to the RPM BRA to recognize weather-related winter risk - Analysis of the RTEP year of 2019/20 to develop winter CETOs and CETLs based on a series of gas outage scenarios. - Evaluation of further scenarios in which greater levels of natural gas will be used to generate electricity and what potential operational issues this could cause, as well as what electric infrastructure will be needed to maintain reliability. | Presentation- Assessment of Winter LOLE Risk at the RTO Level Presentation- Winter Generation Outage Analysis
Gas Infrastructure Future Adequacy | Target 1- Baseline systems draft report has been posted Target 2 initial modeling runs to determine the adequacy of the pipeline infrastructure to meet electric system needs are scheduled to be delivered to Planning Authorities for review by 9/1 | Study results by 2014 | PC | EIPC Gas-Electric System Interface Study includes four Targets: 1. Baseline systems (posted) 2. Infrastructure capability (October) 3. Contingency analysis (December) 4. Dual-Fuel evaluation (November) | Presentation- EIPC Gas-Electric System Interface Study Update
Communications & Procedures | PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alerts. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Waivers | COMPLETE Implemented 6/1 with the new version of M-13 to clarify that PJM does not grant environmental waivers but will work with the GO if requested/notified of limitations. | November-14 June- 14 | OC | Confirm mechanism by which Generation Owners work with PJM during resources seek waivers for fuel emission limitations and better understand conditions under which relief may be granted. | PJM Manual 13
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated October 6, 2014

## HW 11-14 (hidden)
Hot Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials | Hot Weather Report Recommendation Mapping ID
Behind the Meter Generation | Communication plan in review | 2014-12-01 | OC | Establish and document PJM's approach for representing known Behind the Meter generation and the related operating criteria for Dispatchers. This effort will require coordination with the TOs and the States. |  | 7
Unit Characteristics | This overlaps with the cold weather recommendation for Unit Characteristics. See the Cold Weather Recommendation Matrix for status notes | 2014-12-01 | OC | Develop and implement a process for validating generator performance data (ecomax, emergency max, spin max, etc.) |  | 20
PJM Cascading Outage Analysis Procedure | A tool to automate trending for potential cascading contingencies is under development. | 2014-12-15 | SOS / OC | Review PJM's Cascading Outage Analysis procedure and determine how it can be improved as well as automated. |  | 6
System Modeling | Draft documentation on the practices and processes is currently under review. | 2014-12-31 | MC Webinar / Data Management Subcommittee / OC | Update PJM's modeling processes and practices to include PJM's expectations of Transmissions Owners' input; as well the approach to implementing modelling and telemetry across the transmission and sub-transmission system. |  | 1
Emergency Procedures Tool | EP refresh is slated for Q1 of 2015. Will only be filterable by State. County will not be possible until a future timeframe. | Q1 2015 |  | Adding filtering capability to the electronic notification tool to allow PJM staff and stakeholders to determine the applicability of messages they receive. Work with SOS-T (or, capture from DIMA project) to acquire appropriate County/State level info for each Substation/Load in the EMS Model Conduct training for dispatch as needed |  | 17
Facility Limits | External review with MISO and NYISO is complete.External reviews are complete. Impacted MISO facilities are noted on single line diagrams in the PJM EMS. Load Dump Rating Methodology follow-up given at September, October and November SOS/OC meetings. PJM is working with TOs to develop a plan to submit revised ratings for impacted facilities in TERM in order for PJM Markets to run simulations to determine impact. PJM is working with TO on formalizing an implementation plan with a targeted completion date of 6/1/15. | June-15 | SOS-T | Review Facility limits with neighboring companies for pre- and post- contingency information. |  | 4
Synchronized Reserves | Internal meeting scheduled for Q4 2014 to review scope for Instantaneous Reserve Check (IRC) Tool refresh project | 2015-06-01 |  | Improve current methods of providing PJM dispatchers with an accurate presentation of the available reserves on the system at any given time both at an aggregate level and unit-specific. |  | 12
Synchronized Reserves | Instantaneous Reserve Check change is scheduled to be a 2015 Operations project. | 2015-09-01 |  | Review the current Instantaneous Reserve Check (IRC) mechanism for improvements; and identify methods for improving the quality of data being reported by GOs, including reinforcement through training. |  | 11
Demand Response | COMPLETE 10/14 Tool to visualize the location and MW of DR relief has been implemented. | 2014-10-24 | PJM Internal | Develop tools to aid the dispatchers in visualization of the location and MW relief from DR |  | 15
PJM EMS Non-Converge Procedures and Tools | COMPLETED: 9/14 Tool to investigate non-converge SA results has been delivered. PJM tools and modeling was verified for data accuracy | 2014-08-01 |  | Review PJM EMS non-converge procedures and EMS tools to present non-converge situations to PJM operators to include troubleshooting processes. |  | 9
Synchronized Reserves | COMPLETE: 8/14 Tier 1 calculations are being utilized to reflect available reserves | 2014-07-01 | OC / Member Dispatcher Training | Review and modify Tier 1 reserve calculations to more accurately reflect the available reserves from synchronized generating units |  | 10
Communication and Notification Protocols | COMPLETED: 7/14 Training completed for PJM and Member Dispatchers on M1 directive language | 2015-05-15 | OC / Member Dispatcher Training | Enhance tools, documentation, and training to improve communication and notification processes during crises: -Document PJM crisis communication policies -Manual 1 directive language with the PJM and TO Dispatchers |  | 5, 8, 16
PJM EMS Non-Converge and Contingency Management Training | COMPLETE: 7/14 Reinforcement training for operators on contingency management and non-converge situations completed | 2014-07-01 | OC / MC Webinar | Provide reinforcement training for operators on contingency management (contingency trending, PCLLRW, load shed, etc.) in the control room simulator. This this training to look for EMS enhancements for managing constraints |  | 22
Unit Characteristics | COMPLETE: 7/14 This overlaps with the cold weather recommendation for Unit Characteristics. Sorting functionality in the Dispatcher Management Tool has been completed | 2014-04-01 | OC | Improve the generation sorting functionality in the Dispatcher Management Tool. Available and max emergency units should be included on the normal sort. Max Emergency units should be flagged for easy identification. |  | 21
Demand Response | COMPLETE: 7/14 PJM load management subzone information updated | 2014-07-01 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members, should define more subzones proactively across the PJM footprint. |  | 14(1)
Demand Response | COMPLETE: 7/14 DR mapping with zip codes completed | 2014-09-14 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members Map Demand Response Resources to nearest substation. |  | 14(2)
System Modeling | COMPLETE: 7/14 Updated PJM's model & telemetry in the impacted areas. | 2014-07-14 | MC Webinar / Data Management Subcommittee / OC | Improve the PJM model and telemetry in the areas where issues were experienced during the events of September 9 - 11, as needed. |  | 2
Emergency Procedures Tool | COMPLETE: 6/14 Manual 13 revisions are completed | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (1) Develop process language for logging local shed events |  | 8(1)
Emergency Procedures Tool | COMPLETE: 6/14 Training completed in Cycle 4 training | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (2) Develop training to reinforce process and tools |  | 8(2)
Emergency Procedures Tool | COMPLETE: 6/14 Contact list reviewed and training has been completed | 2014-04-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (3) Ensure contact lists are updated and stakeholder are enrolled properly |  | 8(3)
Demand Response | COMPLETE: 5/14 Demand Response filing submitted and approved by the FERC in May 2014 MRC approved Manual 11, 13, and 18 changes for June 1 and dispatcher member training have been completed | 2014-05-01 |  | Implement through the stakeholder process to improve Demand Response operational flexibility to include shorter lead time; sub zonal calls, calls outside of emergencies, and shorter minimum run times. |  | 13
Load Forecasting | COMPLETE: 4/14 Hot and Cold Weather alert process training and manual updates have been completed | 2014-12-15 | OC | Review the current process of handling notification of load forecast errors as well as improving Dispatcher processes for modifying the load forecast when load forecast errors are identified and hot and cold weather alerts considered. 'Review the processes for conducting weather and load forecasting, with consideration for sampling and weighting of weather data throughout the RTO footprint; and methods of developing load forecasts on a sub zonal basis. |  | 18, 19
Operation Guide (Pigeon River) | COMPLETE: 3/14 Operation Guide has been updated and reviewed with the impacted parties and posted to the PJM Internal Dispatcher website. | 2014-02-28 | PJM Internal | Update the Operation guide with relay limits and pre-contingency load shed procedures for Pigeon River. |  | 3
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated November 3, 2014

## HW 10-14 (hidden)
Hot Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials | Hot Weather Report Recommendation Mapping ID
Demand Response | Development in progress for a tool to visualize the location and MW of relief of DR | 9/1/2014 10/24/14 | PJM Internal | Develop tools to aid the dispatchers in visualization of the location and MW relief from DR |  | 15
Behind the Meter Generation | Internal PJM discussions to begin in August 2014. Communication plan in review | 3/15/2015 12/1/14 | OC | Establish and document PJM's approach for representing known Behind the Meter generation and the related operating criteria for Dispatchers. This effort will require coordination with the TOs and the States. |  | 7
Unit Characteristics | This overlaps with the cold weather recommendation for Unit Characteristics. See the Cold Weather Recommendation Matrix for status notes | 2014-12-01 | OC | Develop and implement a process for validating generator performance data (ecomax, emergency max, spin max, etc.) |  | 20
PJM Cascading Outage Analysis Procedure | A tool to automate trending for potential cascading contingencies is under development. | 2014-12-15 | SOS / OC | Review PJM's Cascading Outage Analysis procedure and determine how it can be improved as well as automated. |  | 6
System Modeling | Draft documentation on the practices and processes is currently under review. | 2014-12-31 | MC Webinar / Data Management Subcommittee / OC | Update PJM's modeling processes and practices to include PJM's expectations of Transmissions Owners' input; as well the approach to implementing modelling and telemetry across the transmission and sub-transmission system. |  | 1
Emergency Procedures Tool | Filtering capabilities by County/State for substations in the electronic notification tool will be included in upcoming enhancement project EP refresh is slated for Q1 of 2015. Will only be filterable by State. County will not be possible until a future timeframe. | 12/1/2014 Q1 2015 |  | Adding filtering capability to the electronic notification tool to allow PJM staff and stakeholders to determine the applicability of messages they receive. Work with SOS-T (or, capture from DIMA project) to acquire appropriate County/State level info for each Substation/Load in the EMS Model Conduct training for dispatch as needed |  | 17
Facility Limits | External review with MISO and NYISO is complete. Work with other facilities is still in progress External reviews are complete. Impacted MISO facilities are noted on single line diagrams in the PJM EMS. Load Dump Rating Methodology proposal reviewed at the 8/27 SOS-T. Additional work for Manual 3 update, TERM modifications, and Setting deadlines for initial submission of new ratings is in progress. Load Dump Rating Methodology follow-up given at last SOS meeting on 9/24. TOs will submit revised ratings for impacted facilities in TERM by November 1st. Markets will run simulations to determine impact. Ratings for those facilities that have no Markets impact (the majority) will be implemented by 12/31/14. Those facilities that do have an impact will be implemented on 6/1/15.. | 12/1/2014 June-15 | SOS-T | Review Facility limits with neighboring companies for pre- and post- contingency information. |  | 4
Synchronized Reserves | Internal meeting scheduled for Q4 2014 to review scope for Instantaneous Reserve Check (IRC) Tool refresh project | 2015-06-01 |  | Improve current methods of providing PJM dispatchers with an accurate presentation of the available reserves on the system at any given time both at an aggregate level and unit-specific. |  | 12
Synchronized Reserves | Instantaneous Reserve Check change is scheduled to be a 2015 Operations project. | 2015-09-01 |  | Review the current Instantaneous Reserve Check (IRC) mechanism for improvements; and identify methods for improving the quality of data being reported by GOs, including reinforcement through training. |  | 11
PJM EMS Non-Converge Procedures and Tools | COMPLETED: 9/14 Tool to investigate non-converge SA results has been delivered. PJM tools and modeling was verified for data accuracy | 2014-08-01 |  | Review PJM EMS non-converge procedures and EMS tools to present non-converge situations to PJM operators to include troubleshooting processes. |  | 9
Synchronized Reserves | COMPLETE: 8/14 Tier 1 calculations are being utilized to reflect available reserves | 2014-07-01 | OC / Member Dispatcher Training | Review and modify Tier 1 reserve calculations to more accurately reflect the available reserves from synchronized generating units |  | 10
Communication and Notification Protocols | COMPLETED: 7/14 Training completed for PJM and Member Dispatchers on M1 directive language | 2015-05-15 | OC / Member Dispatcher Training | Enhance tools, documentation, and training to improve communication and notification processes during crises: -Document PJM crisis communication policies -Manual 1 directive language with the PJM and TO Dispatchers |  | 5, 8, 16
PJM EMS Non-Converge and Contingency Management Training | COMPLETE: 7/14 Reinforcement training for operators on contingency management and non-converge situations completed | 2014-07-01 | OC / MC Webinar | Provide reinforcement training for operators on contingency management (contingency trending, PCLLRW, load shed, etc.) in the control room simulator. This this training to look for EMS enhancements for managing constraints |  | 22
Unit Characteristics | COMPLETE: 7/14 This overlaps with the cold weather recommendation for Unit Characteristics. Sorting functionality in the Dispatcher Management Tool has been completed | 2014-04-01 | OC | Improve the generation sorting functionality in the Dispatcher Management Tool. Available and max emergency units should be included on the normal sort. Max Emergency units should be flagged for easy identification. |  | 21
Demand Response | COMPLETE: 7/14 PJM load management subzone information updated | 2014-07-01 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members, should define more subzones proactively across the PJM footprint. |  | 14(1)
Demand Response | COMPLETE: 7/14 DR mapping with zip codes completed | 2014-09-14 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members Map Demand Response Resources to nearest substation. |  | 14(2)
System Modeling | COMPLETE: 7/14 Updated PJM's model & telemetry in the impacted areas. | 2014-07-14 | MC Webinar / Data Management Subcommittee / OC | Improve the PJM model and telemetry in the areas where issues were experienced during the events of September 9 - 11, as needed. |  | 2
Emergency Procedures Tool | COMPLETE: 6/14 Manual 13 revisions are completed | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (1) Develop process language for logging local shed events |  | 8(1)
Emergency Procedures Tool | COMPLETE: 6/14 Training completed in Cycle 4 training | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (2) Develop training to reinforce process and tools |  | 8(2)
Emergency Procedures Tool | COMPLETE: 6/14 Contact list reviewed and training has been completed | 2014-04-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (3) Ensure contact lists are updated and stakeholder are enrolled properly |  | 8(3)
Demand Response | COMPLETE: 5/14 Demand Response filing submitted and approved by the FERC in May 2014 MRC approved Manual 11, 13, and 18 changes for June 1 and dispatcher member training have been completed | 2014-05-01 |  | Implement through the stakeholder process to improve Demand Response operational flexibility to include shorter lead time; sub zonal calls, calls outside of emergencies, and shorter minimum run times. |  | 13
Load Forecasting | COMPLETE: 4/14 Hot and Cold Weather alert process training and manual updates have been completed | 2014-12-15 | OC | Review the current process of handling notification of load forecast errors as well as improving Dispatcher processes for modifying the load forecast when load forecast errors are identified and hot and cold weather alerts considered. 'Review the processes for conducting weather and load forecasting, with consideration for sampling and weighting of weather data throughout the RTO footprint; and methods of developing load forecasts on a sub zonal basis. |  | 18, 19
Operation Guide (Pigeon River) | COMPLETE: 3/14 Operation Guide has been updated and reviewed with the impacted parties and posted to the PJM Internal Dispatcher website. | 2014-02-28 | PJM Internal | Update the Operation guide with relay limits and pre-contingency load shed procedures for Pigeon River. |  | 3
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated October 6, 2014

## CW 11-14 (hidden)
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Cold Weather Resource Performance Improvement | Solution package endorsed at October OC and approved at the 10/30 MRC | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Gas Unit Commitment Coordination | First read completed at the 10/30 MRC and planned for OC endorsement on 11/6 | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | The Energy and Reserve Pricing transition proposal was approved at the October 30 MRC meeting. The Interchange Volatility proposal was not approved at the 10/30 MRC. The ERPIV has been charged with meeting one time to refine the Interchange Volatility proposal and return to the November 20 MRC meeting for another vote. | Short term solution implemented June 1 through September 30; Long term solutions to be voted on at October MIC/MRC and November MC, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Determine whether enhancements can be made to existing rules for transaction scheduling to improve system and price stability | Problem Statement | Issue Charge
Energy Market Uplift | The group continues to discuss methodologies for cost allocation with the target of voting on them in the Fall. PJM has put forward a new proposal that more closely mimics the current allocation methodology with minor changes. The original proposal was not supported by stakeholders and therefore will likely get dropped. | April 1 2015 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Capacity Performance | Comments from initial whitepaper have been posted. Updated whitepaper will be posted on 10/7.Enhanced LC meeting with the Board on 11/4 | TBD | Enhanced Liaison Committee Process | The Problem Definition: Need to refine the definition of capacity •Fuel security – dependable fuel source •Performance incentives and penalties •Capacity resources must be highly available for operations •Require flexible unit operational parameters | Problem Statement | Capacity Performance Proposal
Unit Characteristics | Survey will be sent out in October. Survey responses are due 11/7 | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. FERC is finalizing the NOPR, the comment period closes on 11/28. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Unit Market Offers | Items from this issue will be discussed with Capacity Performance | TBD 2014-2015 Winter | Enhanced Liaison Committee Process | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Offer Caps | The CRSTF was approved for sunsetting at the 10/30 MRC. | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Data Sharing with Gas Industry | Internal PJM effort that is in progress will include: -Improvement of internal FERC 787 data sharing process which includes data sharing for informational purposes -Development of a template, in collaboration with other ISO/RTOs, to facilitate sharing of electric industry operational information and gas pipeline information between the two industries (Draft template to discussed at the meeting with INGAA on 9/3) -Internal dashboard of electrical interconnection areas impacted by pipeline issues (v. 1.0 to be released internally by end of November) | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Interregional Coordination | COMPLETE: -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC -Mutual emergency procedure language in the VACAR/PJM RC Agreement completed IN PROGRESS: - The new EMS display for VACAR reserves will be available by 12/1/14. | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
Voltage Reduction Emergency Procedure | Survey distributed to Transmission Owners and responses being presented back to stakeholders. Data being finalized. Survey responses from TOs utilized to create Voltage reduction plans. Voltage reduction plans have been added to the Dispatcher SharePoint site. First read of edits completed at the 10/30 MRC to be effective for 1/1/15 | 2014-10-01 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
Regulation Market Rules | PJM is in the process of drafting a whitepaper to provide clarification and reasoning on the Regulation Market Rules enhancement recommendations. | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
External Capacity | Tool has been developed and is in the testing phase | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Winter Outage Rate and Reserve planning studies | Internal analysis has started to quantify the impact of higher forced outage rates on future IRM requirements COMPLETE: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 was completed and reviewed at the PC and Capacity Performance mtgs. -Gas outage scenarios development was completed -CETO analysis for the three gas outage scenarios is complete. IN PROGRESS: CETL work is in progress. -CETO/CETL work is in progress -Evaluation of further scenarios and potential operational issues where natural gas will be used to generate electricity is in progress | TBD | Planning Committee | This work consists of the following items: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 -Analysis of the 2018/19 Delivery Year to develop possible recommendations regarding changes to the RPM BRA to recognize weather-related winter risk - Analysis of the RTEP year of 2019/20 to develop winter CETOs and CETLs based on a series of gas outage scenarios. - Evaluation of further scenarios in which greater levels of natural gas will be used to generate electricity and what potential operational issues this could cause, as well as what electric infrastructure will be needed to maintain reliability. | Presentation- Assessment of Winter LOLE Risk at the RTO Level Presentation- Winter Generation Outage Analysis
Gas Infrastructure Future Adequacy | Target 1- Baseline systems draft report has been posted Target 2 initial modeling runs to determine the adequacy of the pipeline infrastructure to meet electric system needs are scheduled to be delivered to Planning Authorities for review by 9/1Posting of the Gas-Electric System Interface Study Target 2 Draft Report has been delayed. The study consultant provided the draft in accordance with the study schedule, however, EIPC learned that additional review was required before it could be posted. EIPC will notify the Stakeholder Steering Committee and stakeholders when the Draft Report is available and if changes to the remaining study schedule are required. | Study results by 2014 | PC | EIPC Gas-Electric System Interface Study includes four Targets: 1. Baseline systems (posted) 2. Infrastructure capability (October) (TBD) 3. Contingency analysis (December) (TBD) 4. Dual-Fuel evaluation (November) (Draft release beginning of November) | Presentation- EIPC Gas-Electric System Interface Study Update
Communications & Procedures | PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alert. Process and procedures to be utilized at the 11/18/14 Winter Emergency drill. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Public Appeals | COMPLETE: Internal discussions completed to determine the impact of Public Appeals on RTO load: At this time there is no accurate method utilized in the industry to determine the impact. No updates will be completed to M13 IN PRORESS: Draft updates to M-13 in progress. | 10/1/2014 1/1/15 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
Waivers | COMPLETE Implemented 6/1 with the new version of M-13 to clarify that PJM does not grant environmental waivers but will work with the GO if requested/notified of limitations. | November-14 June- 14 | OC | Confirm mechanism by which Generation Owners work with PJM during resources seek waivers for fuel emission limitations and better understand conditions under which relief may be granted. | PJM Manual 13
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated November 3, 2014

## HW 12-14 (hidden)
Hot Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials | Hot Weather Report Recommendation Mapping ID
Behind the Meter Generation | Communication plan in review Discussions with pilot states are scheduled to begin in Jan 2015. | 2014-12-01 | OC | Establish and document PJM's approach for representing known Behind the Meter generation and the related operating criteria for Dispatchers. This effort will require coordination with the TOs and the States. |  | 7
Unit Characteristics | This overlaps with the cold weather recommendation for Unit Characteristics. See the Cold Weather Recommendation Matrix for status notes | 2014-12-01 | OC | Develop and implement a process for validating generator performance data (ecomax, emergency max, spin max, etc.) |  | 20
PJM Cascading Outage Analysis Procedure | A tool to automate trending for potential cascading contingencies is under developmenthas been delivered by the vendor and is being tested | 2014-12-15 | SOS / OC | Review PJM's Cascading Outage Analysis procedure and determine how it can be improved as well as automated. |  | 6
System Modeling | Draft documentation on the practices and processes is currently under review. | 2014-12-31 | MC Webinar / Data Management Subcommittee / OC | Update PJM's modeling processes and practices to include PJM's expectations of Transmissions Owners' input; as well the approach to implementing modelling and telemetry across the transmission and sub-transmission system. |  | 1
Emergency Procedures Tool | EP refresh is slated for Q1 of 2015. Will only be filterable by State. County will not be possible until a future timeframe. | Q1 2015 |  | Adding filtering capability to the electronic notification tool to allow PJM staff and stakeholders to determine the applicability of messages they receive. Work with SOS-T (or, capture from DIMA project) to acquire appropriate County/State level info for each Substation/Load in the EMS Model Conduct training for dispatch as needed |  | 17
Facility Limits | External review with MISO and NYISO is complete.External reviews are complete. Impacted MISO facilities are noted on single line diagrams in the PJM EMS. Load Dump Rating Methodology follow-up given at September, October and November SOS/OC meetings. PJM is working with TOs to develop a plan to submit revised ratings for impacted facilities in TERM in order for PJM Markets to run simulations to determine impact. PJM is working with TO on formalizing an implementation plan with a targeted completion date of 6/1/15. | June-15 | SOS-T | Review Facility limits with neighboring companies for pre- and post- contingency information. |  | 4
Synchronized Reserves | Internal meeting scheduled for Q4 2014 to review scope for Instantaneous Reserve Check (IRC) Tool refresh project | 2015-06-01 |  | Improve current methods of providing PJM dispatchers with an accurate presentation of the available reserves on the system at any given time both at an aggregate level and unit-specific. |  | 12
Synchronized Reserves | Instantaneous Reserve Check change is scheduled to be a 2015 Operations project. | 2015-09-01 |  | Review the current Instantaneous Reserve Check (IRC) mechanism for improvements; and identify methods for improving the quality of data being reported by GOs, including reinforcement through training. |  | 11
Demand Response | COMPLETE 10/14 Tool to visualize the location and MW of DR relief has been implemented. | 2014-10-24 | PJM Internal | Develop tools to aid the dispatchers in visualization of the location and MW relief from DR |  | 15
PJM EMS Non-Converge Procedures and Tools | COMPLETED: 9/14 Tool to investigate non-converge SA results has been delivered. PJM tools and modeling was verified for data accuracy | 2014-08-01 |  | Review PJM EMS non-converge procedures and EMS tools to present non-converge situations to PJM operators to include troubleshooting processes. |  | 9
Synchronized Reserves | COMPLETE: 8/14 Tier 1 calculations are being utilized to reflect available reserves | 2014-07-01 | OC / Member Dispatcher Training | Review and modify Tier 1 reserve calculations to more accurately reflect the available reserves from synchronized generating units |  | 10
Communication and Notification Protocols | COMPLETED: 7/14 Training completed for PJM and Member Dispatchers on M1 directive language | 2015-05-15 | OC / Member Dispatcher Training | Enhance tools, documentation, and training to improve communication and notification processes during crises: -Document PJM crisis communication policies -Manual 1 directive language with the PJM and TO Dispatchers |  | 5, 8, 16
PJM EMS Non-Converge and Contingency Management Training | COMPLETE: 7/14 Reinforcement training for operators on contingency management and non-converge situations completed | 2014-07-01 | OC / MC Webinar | Provide reinforcement training for operators on contingency management (contingency trending, PCLLRW, load shed, etc.) in the control room simulator. This this training to look for EMS enhancements for managing constraints |  | 22
Unit Characteristics | COMPLETE: 7/14 This overlaps with the cold weather recommendation for Unit Characteristics. Sorting functionality in the Dispatcher Management Tool has been completed | 2014-04-01 | OC | Improve the generation sorting functionality in the Dispatcher Management Tool. Available and max emergency units should be included on the normal sort. Max Emergency units should be flagged for easy identification. |  | 21
Demand Response | COMPLETE: 7/14 PJM load management subzone information updated | 2014-07-01 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members, should define more subzones proactively across the PJM footprint. |  | 14(1)
Demand Response | COMPLETE: 7/14 DR mapping with zip codes completed | 2014-09-14 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members Map Demand Response Resources to nearest substation. |  | 14(2)
System Modeling | COMPLETE: 7/14 Updated PJM's model & telemetry in the impacted areas. | 2014-07-14 | MC Webinar / Data Management Subcommittee / OC | Improve the PJM model and telemetry in the areas where issues were experienced during the events of September 9 - 11, as needed. |  | 2
Emergency Procedures Tool | COMPLETE: 6/14 Manual 13 revisions are completed | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (1) Develop process language for logging local shed events |  | 8(1)
Emergency Procedures Tool | COMPLETE: 6/14 Training completed in Cycle 4 training | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (2) Develop training to reinforce process and tools |  | 8(2)
Emergency Procedures Tool | COMPLETE: 6/14 Contact list reviewed and training has been completed | 2014-04-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (3) Ensure contact lists are updated and stakeholder are enrolled properly |  | 8(3)
Demand Response | COMPLETE: 5/14 Demand Response filing submitted and approved by the FERC in May 2014 MRC approved Manual 11, 13, and 18 changes for June 1 and dispatcher member training have been completed | 2014-05-01 |  | Implement through the stakeholder process to improve Demand Response operational flexibility to include shorter lead time; sub zonal calls, calls outside of emergencies, and shorter minimum run times. |  | 13
Load Forecasting | COMPLETE: 4/14 Hot and Cold Weather alert process training and manual updates have been completed | 2014-12-15 | OC | Review the current process of handling notification of load forecast errors as well as improving Dispatcher processes for modifying the load forecast when load forecast errors are identified and hot and cold weather alerts considered. 'Review the processes for conducting weather and load forecasting, with consideration for sampling and weighting of weather data throughout the RTO footprint; and methods of developing load forecasts on a sub zonal basis. |  | 18, 19
Operation Guide (Pigeon River) | COMPLETE: 3/14 Operation Guide has been updated and reviewed with the impacted parties and posted to the PJM Internal Dispatcher website. | 2014-02-28 | PJM Internal | Update the Operation guide with relay limits and pre-contingency load shed procedures for Pigeon River. |  | 3
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated December 2, 2014

## CW 12-14 (hidden)
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Gas Unit Commitment Coordination | First read completed at the 10/30 MRC and planned for OC endorsement on 11/6 Scope approved at the 11/20 MRC, Vender Development is In Progress. | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | The Energy and Reserve Pricing transition proposal was approved at the October 30 MRC meeting. The Interchange Volatility proposal was not approved at the 10/30 MRC. The ERPIV has been charged with meeting one time to refine the Interchange Volatility proposal and return to the November 20 MRC meeting for another vote.The updated Interchange Volatility proposal was approved at the 11/20 MRC | Short term solution implemented June 1 through September 30; Long term solutions to be voted on at October MIC/MRC and November MC, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Determine whether enhancements can be made to existing rules for transaction scheduling to improve system and price stability | Problem Statement | Issue Charge
Energy Market Uplift | The group continues to discuss methodologies for cost allocation with the target of voting on them in the Fall. PJM has put forward a new proposal that more closely mimics the current allocation methodology with minor changes. The original proposal was not supported by stakeholders and therefore will likely get dropped. | April 1 2015 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Capacity Performance | The Board of Managers has not yet reached a decision regarding the proposal. They are meeting week of 12/1 and may come to a decision then. They have committed to notifying stakeholders upon reaching their decision and prior to any related filings. | TBD | Enhanced Liaison Committee Process | The Problem Definition: Need to refine the definition of capacity •Fuel security – dependable fuel source •Performance incentives and penalties •Capacity resources must be highly available for operations •Require flexible unit operational parameters | Problem Statement | Capacity Performance Proposal
Unit Characteristics | Survey responses are due 11/7. Responses have been received and data mapping is in progress | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. FERC is finalizing the NOPR, the comment period closes on 11/28. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Data Sharing with Gas Industry | Internal PJM effort that is in progress will include: -Improvement of internal FERC 787 data sharing process which includes data sharing for informational purposes -Internal dashboard of electrical interconnection areas impacted by pipeline issues (v. 1.0 was internally released end of November)Dashboard was delayed until end of Dec., but a coordination team and room as been set up to faciliate gas-electric coordination | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Offer Caps | The CRSTF was approved for sunsetting at the 10/30 MRC. | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Voltage Reduction Emergency Procedure | Survey distributed to Transmission Owners and responses being presented back to stakeholders. Data being finalized. Survey responses from TOs utilized to create Voltage reduction plans. Voltage reduction plans have been added to the Dispatcher SharePoint site. First read of edits completed at the 10/30 MRC . Edits approved to be effective for 1/1/15. | 2014-10-01 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
Interregional Coordination | COMPLETE: -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC -Mutual emergency procedure language in the VACAR/PJM RC Agreement completed IN PROGRESS: - The new EMS display for VACAR reserves will be available by 12/1/14.Displays are available in PCT and are currently being tested | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
External Capacity | Tool has been developed and is in the testing phase Process is in place for external capacity availability and actual performance measurement. | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Gas Infrastructure Future Adequacy | Target 1- Baseline systems draft report has been posted Posting of the Gas-Electric System Interface Study Target 2 Draft Report has been delayed. The study consultant provided the draft in accordance with the study schedule, however, EIPC learned that additional review was required before it could be posted. EIPC will notify the Stakeholder Steering Committee and stakeholders when the Draft Report is available and if changes to the remaining study schedule are required. | Study results by 2014 | PC | EIPC Gas-Electric System Interface Study includes four Targets: 1. Baseline systems (posted) 2. Infrastructure capability (October) (TBD) 3. Contingency analysis (December) (TBD) 4. Dual-Fuel evaluation (November) (Draft released 11/14) | Presentation- EIPC Gas-Electric System Interface Study Update
Regulation Market Rules | PJM is in the process of drafting a whitepaper to provide clarification and reasoning on the Regulation Market Rules enhancement recommendations. | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
Communications & Procedures | COMPLETE PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alert. Process and procedures were utilized at the 11/17/14 Winter Emergency drill. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Winter Outage Rate and Reserve planning studies | COMPLETE: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 was completed and reviewed at the PC and Capacity Performance mtgs. -Gas outage scenarios development was completed -CETO analysis for the three gas outage scenarios is complete. -CETL work is complete | TBD | Planning Committee | This work consists of the following items: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 -Analysis of the 2018/19 Delivery Year to develop possible recommendations regarding changes to the RPM BRA to recognize weather-related winter risk - Analysis of the RTEP year of 2019/20 to develop winter CETOs and CETLs based on a series of gas outage scenarios. - Evaluation of further scenarios in which greater levels of natural gas will be used to generate electricity and what potential operational issues this could cause, as well as what electric infrastructure will be needed to maintain reliability. | Presentation- Assessment of Winter LOLE Risk at the RTO Level Presentation- Winter Generation Outage Analysis
Cold Weather Resource Performance Improvement | COMPLETE Process started as of 11/1 | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Unit Market Offers | COMPLETED Items from this issue will be discussed with Capacity Performance | TBD 2014-2015 Winter | Enhanced Liaison Committee Process | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Public Appeals | COMPLETE Internal discussions completed to determine the impact of Public Appeals on RTO load: At this time there is no accurate method utilized in the industry to determine the impact. No updates will be completed to M13 IN PRORESS: Draft updates to M-13 in progress. | 10/1/2014 1/1/15 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
Waivers | COMPLETE Implemented 6/1 with the new version of M-13 to clarify that PJM does not grant environmental waivers but will work with the GO if requested/notified of limitations. | November-14 June- 14 | OC | Confirm mechanism by which Generation Owners work with PJM during resources seek waivers for fuel emission limitations and better understand conditions under which relief may be granted. | PJM Manual 13
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated December 2, 2014

## CW 1-15 (hidden)
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Gas Unit Commitment Coordination | Scope approved at the 11/20 MRC, vender Development is In Progress. Manual process will be put in place on 1/1/15 until automatic functionality is available (planned for 2/9/15) | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | The Energy and Reserve Pricing transition proposal was approved at the October 30 MRC meeting. Starting1/1/15, long lead units will be committed in the DA Market and DASR will be cleared up to economic max rather than emergency max. The primary reserve requirement will be increased to reflect any additional reserves that are scheduled intraday. Effective 3/1/15 (pending FERC approval) the synchronized reserve requirement will also be increased and the second step on the reserve demand curves will be implemented. The increase to the DASR requirement will also become effective at this time. The updated Interchange Volatility proposal was approved at the 11/20 MRC and planned for implementation on 1/1/15. | Short term solution implemented June 1 through September 30; Long term solutions to be voted on at October MIC/MRC and November MC, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Determine whether enhancements can be made to existing rules for transaction scheduling to improve system and price stability | Problem Statement | Issue Charge
Data Sharing with Gas Industry | Internal PJM effort that is in progress will include: -Improvement of internal FERC 787 data sharing process which includes data sharing for informational purposes -Internal dashboard of electrical interconnection areas impacted by pipeline issues- Internal Daily Gas Notification Email was started in Nov. and Weekly Phone Calls with the Pipelines was started in Dec. | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Offer Caps | The CRSTF was approved for sunsetting at the 10/30 MRC. Filing submitted to FERC for the interim cost-based offer cap to be $1,800 and any costs above that to be compensated through after-the-fact review of actual costs | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Gas Infrastructure Future Adequacy | Target 4 Final Draft Report was released in December. | Study results by 2014 | PC | EIPC Gas-Electric System Interface Study includes four Targets: 1. Baseline systems (Posted) 2. Infrastructure capability (October) (TBD) 3. Contingency analysis (December) (TBD) 4. Dual-Fuel evaluation (November) (Released 12/14) | Presentation- EIPC Gas-Electric System Interface Study Update
Unit Characteristics | Responses have been received and data mapping is in progress. Internal report has been developed to view static data. Fuel data will be mapped once fields are available in eMKT. | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Capacity Performance | The filing was submitted to FERC on 12/12/14 with requested effective date 4/1/15. PJM FAQ process has been implemented with responses posted bi-weekly. | 2015-04-15 | Enhanced Liaison Committee Process | The Problem Definition: Need to refine the definition of capacity •Fuel security – dependable fuel source •Performance incentives and penalties •Capacity resources must be highly available for operations •Require flexible unit operational parameters | Problem Statement | Capacity Performance Proposal
Energy Market Uplift | The group continues to discuss methodologies for cost allocation with the target of voting on them in the Fall. PJM has put forward a new proposal that more closely mimics the current allocation methodology with minor changes. The original proposal was not supported by stakeholders and therefore will likely get dropped. | 2015-04-01 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. FERC is finalizing the NOPR, the comment period closes on 11/28. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Regulation Market Rules | PJM is in the process of drafting a whitepaper to provide clarification and reasoning on the Regulation Market Rules enhancement recommendations. | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
Voltage Reduction Emergency Procedure | COMPLETE: 1/15 Survey responses from TOs utilized to create Voltage reduction plans. Voltage reduction plans have been added to the Dispatcher SharePoint site. First read of edits completed at the 10/30 MRC . Edits approved to be effective for 1/1/15. | 10/1/2014 January-15 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
External Capacity | COMPLETE: Tool has been developed and is in the testing phase Process is in place for external capacity availability and actual performance measurement. | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Interregional Coordination | COMPLETE:12/14 -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC -Mutual emergency procedure language in the VACAR/PJM RC Agreement completed -The new version of the EMS Unit Reserve Report was transferred to production and now includes filtering for VACAR | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
Communications & Procedures | COMPLETE: PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alert. Process and procedures were utilized at the 11/17/14 Winter Emergency drill. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Winter Outage Rate and Reserve planning studies | COMPLETE: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 was completed and reviewed at the PC and Capacity Performance mtgs. -Gas outage scenarios development was completed -CETO analysis for the three gas outage scenarios is complete. -CETL work is complete | TBD | Planning Committee | This work consists of the following items: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 -Analysis of the 2018/19 Delivery Year to develop possible recommendations regarding changes to the RPM BRA to recognize weather-related winter risk - Analysis of the RTEP year of 2019/20 to develop winter CETOs and CETLs based on a series of gas outage scenarios. - Evaluation of further scenarios in which greater levels of natural gas will be used to generate electricity and what potential operational issues this could cause, as well as what electric infrastructure will be needed to maintain reliability. | Presentation- Assessment of Winter LOLE Risk at the RTO Level Presentation- Winter Generation Outage Analysis
Cold Weather Resource Performance Improvement | COMPLETE Process started as of 11/1 | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Unit Market Offers | COMPLETED Items from this issue will be discussed with Capacity Performance | TBD 2014-2015 Winter | Enhanced Liaison Committee Process | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Public Appeals | COMPLETE Internal discussions completed to determine the impact of Public Appeals on RTO load: At this time there is no accurate method utilized in the industry to determine the impact. No updates will be completed to M13 IN PRORESS: Draft updates to M-13 in progress. | 10/1/2014 1/1/15 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
Waivers | COMPLETE Implemented 6/1 with the new version of M-13 to clarify that PJM does not grant environmental waivers but will work with the GO if requested/notified of limitations. | November-14 June- 14 | OC | Confirm mechanism by which Generation Owners work with PJM during resources seek waivers for fuel emission limitations and better understand conditions under which relief may be granted. | PJM Manual 13
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated January 1, 2015

## HW 1-15 (hidden)
Hot Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials | Hot Weather Report Recommendation Mapping ID
PJM Cascading Outage Analysis Procedure | A tool to automate trending for potential cascading contingencies has been delivered by the vendor and is being tested. Vendor delivery contained defects and is in the process of being fixed. | 2014-12-15 | SOS / OC | Review PJM's Cascading Outage Analysis procedure and determine how it can be improved as well as automated. |  | 6
System Modeling | Draft documentation on the practices and processes is currently under review and planned for final approval by early 2015. | 12/31/2014 Q1 2015 | MC Webinar / Data Management Subcommittee / OC | Update PJM's modeling processes and practices to include PJM's expectations of Transmissions Owners' input; as well the approach to implementing modelling and telemetry across the transmission and sub-transmission system. |  | 1
Emergency Procedures Tool | EP refresh is slated for Q1 of 2015. Will only be filterable by State. County will not be possible until a future timeframe. | Q1 2015 |  | Adding filtering capability to the electronic notification tool to allow PJM staff and stakeholders to determine the applicability of messages they receive. Work with SOS-T (or, capture from DIMA project) to acquire appropriate County/State level info for each Substation/Load in the EMS Model Conduct training for dispatch as needed |  | 17
Facility Limits | External review with MISO and NYISO is complete.External reviews are complete. Impacted MISO facilities are noted on single line diagrams in the PJM EMS. Load Dump Rating Methodology follow-up given at September, October and November SOS/OC meetings. PJM is working with TOs to develop a plan to submit revised ratings for impacted facilities in TERM in order for PJM Markets to run simulations to determine impact. PJM is working with TO on formalizing an implementation plan with a targeted completion date of 6/1/15. | June-15 | SOS-T | Review Facility limits with neighboring companies for pre- and post- contingency information. |  | 4
Synchronized Reserves | Instantaneous Reserve Check project is scheduled for 2015. | 2015-09-01 |  | Review the current Instantaneous Reserve Check (IRC) mechanism for improvements; and identify methods for improving the quality of data being reported by GOs, including reinforcement through training. Improve current methods of providing PJM dispatchers with an accurate presentation of the available reserves on the system at any given time both at an aggregate level and unit-specific. |  | 11, 12
Unit Characteristics | This overlaps with the cold weather recommendation for Unit Characteristics. See the Cold Weather Recommendation Matrix for status notes | 2014/2015 | OC | Develop and implement a process for validating generator performance data (ecomax, emergency max, spin max, etc.) |  | 20
Behind the Meter Generation | COMPLETED: 12/14 Discussions with pilot states are scheduled to begin in Jan 2015 to review: 1- Issues and work done by PJM so far 2- List of units not under PJM control 3- Discuss possible options | 2014-12-01 | OC | Establish and document PJM's approach for representing known Behind the Meter generation and the related operating criteria for Dispatchers. This effort will require coordination with the TOs and the States. |  | 7
Demand Response | COMPLETE 10/14 Tool to visualize the location and MW of DR relief has been implemented. | 2014-10-24 | PJM Internal | Develop tools to aid the dispatchers in visualization of the location and MW relief from DR |  | 15
PJM EMS Non-Converge Procedures and Tools | COMPLETED: 9/14 Tool to investigate non-converge SA results has been delivered. PJM tools and modeling was verified for data accuracy | 2014-08-01 |  | Review PJM EMS non-converge procedures and EMS tools to present non-converge situations to PJM operators to include troubleshooting processes. |  | 9
Synchronized Reserves | COMPLETE: 8/14 Tier 1 calculations are being utilized to reflect available reserves | 2014-07-01 | OC / Member Dispatcher Training | Review and modify Tier 1 reserve calculations to more accurately reflect the available reserves from synchronized generating units |  | 10
Communication and Notification Protocols | COMPLETED: 7/14 Training completed for PJM and Member Dispatchers on M1 directive language | 2015-05-15 | OC / Member Dispatcher Training | Enhance tools, documentation, and training to improve communication and notification processes during crises: -Document PJM crisis communication policies -Manual 1 directive language with the PJM and TO Dispatchers |  | 5, 8, 16
PJM EMS Non-Converge and Contingency Management Training | COMPLETE: 7/14 Reinforcement training for operators on contingency management and non-converge situations completed | 2014-07-01 | OC / MC Webinar | Provide reinforcement training for operators on contingency management (contingency trending, PCLLRW, load shed, etc.) in the control room simulator. This this training to look for EMS enhancements for managing constraints |  | 22
Unit Characteristics | COMPLETE: 7/14 This overlaps with the cold weather recommendation for Unit Characteristics. Sorting functionality in the Dispatcher Management Tool has been completed | 2014-04-01 | OC | Improve the generation sorting functionality in the Dispatcher Management Tool. Available and max emergency units should be included on the normal sort. Max Emergency units should be flagged for easy identification. |  | 21
Demand Response | COMPLETE: 7/14 PJM load management subzone information updated | 2014-07-01 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members, should define more subzones proactively across the PJM footprint. |  | 14(1)
Demand Response | COMPLETE: 7/14 DR mapping with zip codes completed | 2014-09-14 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members Map Demand Response Resources to nearest substation. |  | 14(2)
System Modeling | COMPLETE: 7/14 Updated PJM's model & telemetry in the impacted areas. | 2014-07-14 | MC Webinar / Data Management Subcommittee / OC | Improve the PJM model and telemetry in the areas where issues were experienced during the events of September 9 - 11, as needed. |  | 2
Emergency Procedures Tool | COMPLETE: 6/14 Manual 13 revisions are completed | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (1) Develop process language for logging local shed events |  | 8(1)
Emergency Procedures Tool | COMPLETE: 6/14 Training completed in Cycle 4 training | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (2) Develop training to reinforce process and tools |  | 8(2)
Emergency Procedures Tool | COMPLETE: 6/14 Contact list reviewed and training has been completed | 2014-04-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (3) Ensure contact lists are updated and stakeholder are enrolled properly |  | 8(3)
Demand Response | COMPLETE: 5/14 Demand Response filing submitted and approved by the FERC in May 2014 MRC approved Manual 11, 13, and 18 changes for June 1 and dispatcher member training have been completed | 2014-05-01 |  | Implement through the stakeholder process to improve Demand Response operational flexibility to include shorter lead time; sub zonal calls, calls outside of emergencies, and shorter minimum run times. |  | 13
Load Forecasting | COMPLETE: 4/14 Hot and Cold Weather alert process training and manual updates have been completed | 2014-12-15 | OC | Review the current process of handling notification of load forecast errors as well as improving Dispatcher processes for modifying the load forecast when load forecast errors are identified and hot and cold weather alerts considered. 'Review the processes for conducting weather and load forecasting, with consideration for sampling and weighting of weather data throughout the RTO footprint; and methods of developing load forecasts on a sub zonal basis. |  | 18, 19
Operation Guide (Pigeon River) | COMPLETE: 3/14 Operation Guide has been updated and reviewed with the impacted parties and posted to the PJM Internal Dispatcher website. | 2014-02-28 | PJM Internal | Update the Operation guide with relay limits and pre-contingency load shed procedures for Pigeon River. |  | 3
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated January 1, 2015

## CW 2-15
Cold Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials |  | Solutions Matrix DOCS #
Gas Unit Commitment Coordination | New eMKT fields were implemented on 1/29/15 in production.Intraday cost schedule update functionality was implemented in Sandbox on 1/27/15 and planned for production on 2/9/15. | Short term changes (prior to the winter of 2014/2015) Long term changes (early 2015) | OC | Improve the clarity, transparency and standardization of handling long-lead gas unit commitment, due to fuel restrictions. Consider tools, processes, market construct, as well as communication and notification protocols. | Problem Statement | Issue Charge
Energy & Reserve Pricing | The Energy and Reserve Pricing transition proposal was approved at the October 30 MRC meeting. Starting1/1/15, long lead units will be committed in the DA Market and DASR will be cleared up to economic max rather than emergency max. The primary reserve requirement will be increased to reflect any additional reserves that are scheduled intraday. Effective 3/1/15 (pending FERC approval) the synchronized reserve requirement will also be increased and the second step on the reserve demand curves will be implemented. The increase to the DASR requirement will also become effective at this time. The updated Interchange Volatility proposal was approved at the 11/20 MRC and implemented on 1/1/15. | Short term solution implemented June 1 through September 30; Long term solutions to be voted on at October MIC/MRC and November MC, Implementation TBD | Energy Reserve Pricing and Interchange Price Volatility Initiative (ERPIV) | Determine whether enhancements can be made to better capture conservative operator actions in market clearing prices: Determine whether enhancements can be made to existing rules for transaction scheduling to improve system and price stability | Problem Statement | Issue Charge
Capacity Performance | The filing was submitted to FERC on 12/12/14 with requested effective date 4/1/15. Member comments were due to FERC by 1/20/15. | 2015-04-15 | Enhanced Liaison Committee Process | The Problem Definition: Need to refine the definition of capacity •Fuel security – dependable fuel source •Performance incentives and penalties •Capacity resources must be highly available for operations •Require flexible unit operational parameters | Problem Statement | Capacity Performance Proposal
Energy Market Uplift | The group continues to discuss methodologies for cost allocation with the target of voting on them in the Fall. PJM has put forward a new proposal that more closely mimics the current allocation methodology with minor changes. The original proposal was not supported by stakeholders and therefore will likely get dropped. | 2015-04-01 | Energy Market Uplift Senior TF (EMUSTF) | Review and consider changes to the following regarding uplift: -Cost allocation of energy market uplift charges, -Potential mechanism to allocation uplift during emergency operations when rates are extreme, and -Additional methods and procedures for reducing the overall amount of uplift to be paid | Problem Statement / Issue Charge
Gas Infrastructure Future Adequacy | Target 2 Final Draft Report was released 1/30/15. | Study results by 2014 July 2015 | PC | EIPC Gas-Electric System Interface Study includes four Targets: 1. Baseline systems (Posted) 2. Infrastructure capability (October) (1/30/15) 3. Contingency analysis (December) (TBD) 4. Dual-Fuel evaluation (November) (Released 12/14) | Presentation- EIPC Gas-Electric System Interface Study Update
Gas / Electric Industry Coordination | PJM is working through the NAESB process, as part of the FERC NOPR. FERC has requested data from PJM to analyze impact of gas and electric day on reliable and efficient operations. | 2015-09-01 | MC Webinar | PJM, in conjunction with stakeholders, is developing industry recommendations for the following topics in response to the FERC NOPR on gas / electric coordination: -Harmonization of the timing of the gas and electric operating days -Will determine PJM market timing to coordinate with gas day and nomination schedules once FERC NOPR is finalized | FERC NOPR
Regulation Market Rules | PJM is in the process of drafting a whitepaper to provide clarification and reasoning on the Regulation Market Rules enhancement recommendations. | TBD | MIC | Reexamine the performance of the Regulation Market based on January results and consider: -Whether the division by the performance score is appropriate, -Whether the minimum participation requirements are adequately high enough -Whether going short on regulation during system peaks is acceptable
Unit Characteristics | COMPLETE: Internal report has been developed to view static data. Fuel data was mapped to new fields deployed in eMKT on 1/29/15. | 2014/2015 | OC | Working with the generation owners to identify opportunities to create or improve information sharing such as fuel source and limitations, emission limitations; as well as use and validation of outage types .
Offer Caps | COMPLETE: 1/16/15 The CRSTF was approved for sunsetting at the 10/30 MRC. Filing submitted to FERC for the interim cost-based offer cap to be $1,800 and any costs above that to be compensated through after-the-fact review of actual costs. Filing EL15-31-000 was accepted by FERC on 1/16/15. | 2014-12-14 | Cap Review Senior Task Force (CRSTF) | Analyze and review generation energy market offer caps for both cost-based and price-based offers. | Problem Statement | Issue Charge
Data Sharing with Gas Industry | COMPLETE: Internal PJM effort that is in progress will include: -Improvement of internal FERC 787 data sharing process which includes data sharing for informational purposes -Internal dashboard of electrical interconnection areas impacted by pipeline issues- Internal Daily Gas Notification Email was started in Nov. and Weekly Phone Calls with the Pipelines was started in Dec. | 2014-11-01 | MC Webinar | Improve the tools and processes for two-way communication with the gas industry to enhance situational awareness and better evaluate impact to PJM generation
Voltage Reduction Emergency Procedure | COMPLETE: 1/15 Survey responses from TOs utilized to create Voltage reduction plans. Voltage reduction plans have been added to the Dispatcher SharePoint site. First read of edits completed at the 10/30 MRC . Edits approved to be effective for 1/1/15. | 10/1/2014 January-15 | SOS-T & OC | Review the voltage reduction capabilities of transmission owners to better understand current capabilities and determine if there are additional requirements to be developed
External Capacity | COMPLETE: Process is in place for external capacity availability and actual performance measurement. | 2014-10-01 | MC Webinar | Develop processes and tools to confirm external capacity resources availability, day-ahead and real-time market commitments, and actual performance.
Interregional Coordination | COMPLETE:12/14 -Emergency Procedure document and contacts created and discussed with VACAR group. - 5/20/14 Summer Emergency drill completed with Duke Energy Progress - Reference guide to support NERC tags for shared reserves created for the Dominion MOC -Mutual emergency procedure language in the VACAR/PJM RC Agreement completed -The new version of the EMS Unit Reserve Report was transferred to production and now includes filtering for VACAR | 2014-07-01 | MC Webinar | Consider improvements to increase situational awareness with the VACAR Reserve Sharing group and VACAR Reliability Coordinator: -Define and review PJM emergency procedures and overall communications, including a review of the operating agreements, including the VACAR Reserve Sharing Group Agreement
Communications & Procedures | COMPLETE: PJM developed an internal Operational Emergency Readiness Team that was deployed during January to facilitate discussions internally and externally. Additional enhancements to be incorporated as part of the Summer and Winter Emergency Procedure drills. OM-004 drafted and posted effective 6/1. Utilized for 5/20/14 Summer drill and recent Hot Weather Alert. Process and procedures were utilized at the 11/17/14 Winter Emergency drill. | 2014-11-14 | MC Webinar | Consider further improvements to internal and external communication tools, processes, and protocols during Operational emergencies.
Winter Outage Rate and Reserve planning studies | COMPLETE: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 was completed and reviewed at the PC and Capacity Performance mtgs. -Gas outage scenarios development was completed -CETO analysis for the three gas outage scenarios is complete. -CETL work is complete | TBD | Planning Committee | This work consists of the following items: -A loss of load probability assessment of the winters of 2014/15 and 2015/16 -Analysis of the 2018/19 Delivery Year to develop possible recommendations regarding changes to the RPM BRA to recognize weather-related winter risk - Analysis of the RTEP year of 2019/20 to develop winter CETOs and CETLs based on a series of gas outage scenarios. - Evaluation of further scenarios in which greater levels of natural gas will be used to generate electricity and what potential operational issues this could cause, as well as what electric infrastructure will be needed to maintain reliability. | Presentation- Assessment of Winter LOLE Risk at the RTO Level Presentation- Winter Generation Outage Analysis
Cold Weather Resource Performance Improvement | COMPLETE Process started as of 11/1 | 2014-10-01 | OC | Improve the performance of resources during extreme cold weather events via some level of performance verification or testing of certain resources during cold weather, including testing dual-fuel capability | Problem Statement | Issue Charge | x
Unit Market Offers | COMPLETED Items from this issue will be discussed with Capacity Performance | 2014-2015 Winter | Enhanced Liaison Committee Process | Consider potential market rule changes that would allow generators to better include natural gas costs in their energy or capacity market offers; and Consider the ability of a unit to make changes to energy market offers during the operating day
Public Appeals | COMPLETE Internal discussions completed to determine the impact of Public Appeals on RTO load: At this time there is no accurate method utilized in the industry to determine the impact. Updates to M13 v.57 were completed | 1/1/15 | MC Webinar | PJM to : -Determine if it is possible to quantify impact of public appeals for conservation and if so, investigate where or how to use this information. -Improve process (triggers, protocols, content, and processes) for public notification during emergency procedures (C1/C2, H1/H2)
Waivers | COMPLETE Implemented 6/1 with the new version of M-13 to clarify that PJM does not grant environmental waivers but will work with the GO if requested/notified of limitations. | June- 14 | OC | Confirm mechanism by which Generation Owners work with PJM during fuel emission limitations and better understand conditions under which relief may be granted. | PJM Manual 13
Emergency Energy Bids | COMPLETE Transition to an electronic form versus fax has been completed and updated in M-13. | M-13 Approved at April & May MRC | OC | Review and enhance the tools and processes for accepting Emergency Energy Bids | PJM Manual 13 - Attachment D
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated February 2, 2015

## HW 2-15
Hot Weather Recommendation Status
Topic | Status and Notes | Implementation Timing | Working Committee | Description | Materials | Hot Weather Report Recommendation Mapping ID
System Modeling | Draft documentation on the practices and processes is currently under review and planned for final approval by early 2015. | 12/31/2014 Q1 2015 | MC Webinar / Data Management Subcommittee / OC | Update PJM's modeling processes and practices to include PJM's expectations of Transmissions Owners' input; as well the approach to implementing modelling and telemetry across the transmission and sub-transmission system. |  | 1
Emergency Procedures Tool | EP refresh is slated for Q1 of 2015. Will only be filterable by State. County will not be possible until a future timeframe. | Q1 2015 |  | Adding filtering capability to the electronic notification tool to allow PJM staff and stakeholders to determine the applicability of messages they receive. Work with SOS-T (or, capture from DIMA project) to acquire appropriate County/State level info for each Substation/Load in the EMS Model Conduct training for dispatch as needed |  | 17
PJM Cascading Outage Analysis Procedure | Vendor delivery contained defects and is in the process of being fixed. Defects have been corrected and are in the process of being deployed for testing | 12/15/2014 Q2 2015 | SOS / OC | Review PJM's Cascading Outage Analysis procedure and determine how it can be improved as well as automated. |  | 6
Facility Limits | External review with MISO and NYISO is complete.External reviews are complete. Impacted MISO facilities are noted on single line diagrams in the PJM EMS. Load Dump Rating Methodology follow-up given at September, October and November SOS/OC meetings. PJM is working with TOs to develop a plan to submit revised ratings for impacted facilities in TERM in order for PJM Markets to run simulations to determine impact. PJM is working with TO on formalizing an implementation plan with a targeted completion date of 6/1/15. | June-15 | SOS-T | Review Facility limits with neighboring companies for pre- and post- contingency information. |  | 4
Synchronized Reserves | Instantaneous Reserve Check project is scheduled for 2015. | 2015-09-01 |  | Review the current Instantaneous Reserve Check (IRC) mechanism for improvements; and identify methods for improving the quality of data being reported by GOs, including reinforcement through training. Improve current methods of providing PJM dispatchers with an accurate presentation of the available reserves on the system at any given time both at an aggregate level and unit-specific. |  | 11, 12
Unit Characteristics | COMPLETE: This overlaps with the cold weather recommendation for Unit Characteristics. See the Cold Weather Recommendation Matrix for status notes | 2014/2015 | OC | Develop and implement a process for validating generator performance data (ecomax, emergency max, spin max, etc.) |  | 20
Behind the Meter Generation | COMPLETE: 12/14 Discussions with pilot states are scheduled to begin in Jan 2015 to review: 1- Issues and work done by PJM so far 2- List of units not under PJM control 3- Discuss possible options | 2014-12-01 | OC | Establish and document PJM's approach for representing known Behind the Meter generation and the related operating criteria for Dispatchers. This effort will require coordination with the TOs and the States. |  | 7
Demand Response | COMPLETE 10/14 Tool to visualize the location and MW of DR relief has been implemented. | 2014-10-24 | PJM Internal | Develop tools to aid the dispatchers in visualization of the location and MW relief from DR |  | 15
PJM EMS Non-Converge Procedures and Tools | COMPLETE: 9/14 Tool to investigate non-converge SA results has been delivered. PJM tools and modeling was verified for data accuracy | 2014-08-01 |  | Review PJM EMS non-converge procedures and EMS tools to present non-converge situations to PJM operators to include troubleshooting processes. |  | 9
Synchronized Reserves | COMPLETE: 8/14 Tier 1 calculations are being utilized to reflect available reserves | 2014-07-01 | OC / Member Dispatcher Training | Review and modify Tier 1 reserve calculations to more accurately reflect the available reserves from synchronized generating units |  | 10
Communication and Notification Protocols | COMPLETE: 7/14 Training completed for PJM and Member Dispatchers on M1 directive language | 2015-05-15 | OC / Member Dispatcher Training | Enhance tools, documentation, and training to improve communication and notification processes during crises: -Document PJM crisis communication policies -Manual 1 directive language with the PJM and TO Dispatchers |  | 5, 8, 16
PJM EMS Non-Converge and Contingency Management Training | COMPLETE: 7/14 Reinforcement training for operators on contingency management and non-converge situations completed | 2014-07-01 | OC / MC Webinar | Provide reinforcement training for operators on contingency management (contingency trending, PCLLRW, load shed, etc.) in the control room simulator. This this training to look for EMS enhancements for managing constraints |  | 22
Unit Characteristics | COMPLETE: 7/14 This overlaps with the cold weather recommendation for Unit Characteristics. Sorting functionality in the Dispatcher Management Tool has been completed | 2014-04-01 | OC | Improve the generation sorting functionality in the Dispatcher Management Tool. Available and max emergency units should be included on the normal sort. Max Emergency units should be flagged for easy identification. |  | 21
Demand Response | COMPLETE: 7/14 PJM load management subzone information updated | 2014-07-01 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members, should define more subzones proactively across the PJM footprint. |  | 14(1)
Demand Response | COMPLETE: 7/14 DR mapping with zip codes completed | 2014-09-14 | PJM Internal | To improve the reliability of using Demand Response for transmission constraints, PJM, in conjunction with Members Map Demand Response Resources to nearest substation. |  | 14(2)
System Modeling | COMPLETE: 7/14 Updated PJM's model & telemetry in the impacted areas. | 2014-07-14 | MC Webinar / Data Management Subcommittee / OC | Improve the PJM model and telemetry in the areas where issues were experienced during the events of September 9 - 11, as needed. |  | 2
Emergency Procedures Tool | COMPLETE: 6/14 Manual 13 revisions are completed | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (1) Develop process language for logging local shed events |  | 8(1)
Emergency Procedures Tool | COMPLETE: 6/14 Training completed in Cycle 4 training | 2014-06-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (2) Develop training to reinforce process and tools |  | 8(2)
Emergency Procedures Tool | COMPLETE: 6/14 Contact list reviewed and training has been completed | 2014-04-01 | PJM Internal | Review how the Emergency Procedures application is used during local load shed events and develop solutions to address the following topics: (3) Ensure contact lists are updated and stakeholder are enrolled properly |  | 8(3)
Demand Response | COMPLETE: 5/14 Demand Response filing submitted and approved by the FERC in May 2014 MRC approved Manual 11, 13, and 18 changes for June 1 and dispatcher member training have been completed | 2014-05-01 |  | Implement through the stakeholder process to improve Demand Response operational flexibility to include shorter lead time; sub zonal calls, calls outside of emergencies, and shorter minimum run times. |  | 13
Load Forecasting | COMPLETE: 4/14 Hot and Cold Weather alert process training and manual updates have been completed | 2014-12-15 | OC | Review the current process of handling notification of load forecast errors as well as improving Dispatcher processes for modifying the load forecast when load forecast errors are identified and hot and cold weather alerts considered. 'Review the processes for conducting weather and load forecasting, with consideration for sampling and weighting of weather data throughout the RTO footprint; and methods of developing load forecasts on a sub zonal basis. |  | 18, 19
Operation Guide (Pigeon River) | COMPLETE: 3/14 Operation Guide has been updated and reviewed with the impacted parties and posted to the PJM Internal Dispatcher website. | 2014-02-28 | PJM Internal | Update the Operation guide with relay limits and pre-contingency load shed procedures for Pigeon River. |  | 3
CERA D796478
On target for vote date.
Vote date threatened.
Unlikely to meet vote date.
Updated February 2, 2015