## Instructions
Proposal Template Instructions
General Instructions
Upgrade project requirements: Complete tabs 1, 2, 3, 9 and the appropriate tab 4 or 5 for each project component as identified on tab 3.
Greenfield project requirements: Complete tabs 1, 2, 3, 9 and the appropriate tabs 4 through 7 for each project component as identified on tab 3.
Component Tabs (4-7): When the project scope includes multiple components of the same type, copy the appropriate tab types needed to fully detail the project components.
Redaction: PJM's redaction guidelines are posted on pjm.com at the link below. Redacted files should be provided with the completed template and identified on the appropriate tab. If other responses or portions of responses are deemed proprietary, they can be included on the 'Redacted Information' tab with a reference back to the response identification number.
http://pjm.com/~/media/planning/rtep-dev/expan-plan-process/ferc-order-1000/rtep-proposal-windows/proposal-redaction-guidelines.ashx
Cost Containment: Proposals submitting a cost containment commitment are required to complete the '10. Cost Contain' tab.
1. | Executive Summary Tab
| 1.a. | Provide the name of the Proposing Entity. If there are multiple entities, please identify each party.
| 1.b. | Provide the RTEP Proposal Window in which this proposal is being submitted.
| 1.c. | Provide the Proposing Entity project proposal id. Use "A, B, C, …", etc. to differentiate between proposals.
| 1.d. | Provide a General Description of the scope of this project, including the associated violation/issue being addressed and the type of regional/interregional analysis or process that identified the violation/issue.
| 1.e. | Identify if the proposal or a proposal component span between two PJM Transmission Owner zones. This group includes transmission that spans two or more affiliated companies (e.g. Meted and Allegheny Power).
| 1.f. | Indicate if the project is being proposed as a solution to a Cross-Border issue. (Note: The Proposing Entity is responsible for initiating and satisfying all Regional and Interregional requirements.)
| 1.g. | Indicate if the Proposing Entity intends to construct, own, operate, and maintain the infrastructure built under this proposal.
| 1.h. | Provide a description of how the project should be considered; only as a whole or if portions of the project should be considered as well. (Separable portions/combinations should be submitted as separate proposals. If a proposal is submitted with multiple options, PJM will split it into multiple proposals. PJM reserves the right to select the best project, regardless of how it is packaged by Proposing Entities.)
| 1.i. | Total current year project cost estimate including estimates for any required Transmission Owner upgrades.
| 1.j. | Total in-service year project cost estimate including estimates for any required Transmission Owner upgrades.
| 1.k. | Project estimated schedule duration in months.
| 1.l. | Indicate if any cost containment commitment is being proposed as part of the project. If yes, the "Cost Containment" tab within this project proposal template is to be completed
| 1.m. | If the project provides any additional benefits above solving the identified violations or constraints, identify those benefits.
If the answer to the Cross-Border question above at 1.f. was yes, complete the questions below.
| 1.n.i. | Indicate if an evaluation for Interregional Cost Allocation is desired.
| 1.n.ii. | Indicate if the proposal has been evaluated in a coordinated interregional analysis under the PJM Tariff or Operating Agreement provisions. Specify the analysis and applicable Tariff or Operating Agreement provisions.
| 1.n.iii. | List the specific Regional and Interregional violations and issues from the Regional and/or Interregional analyses that identified the violations and issues addressed by the proposal.
2. | Overloaded Facilities Tab
| 2.a. | Identify the criteria violation(s) or system constraint(s) that the proposed project solves or mitigates.
| 2.b. | Identify the criteria violation(s) or system constraint(s) that the proposed project causes or does not address.
3. | Project Components Tab
| 3.a. | Provide a description for each project component. Each project component will require the completion of the tab corresponding to the category of the component ("Greenfield Substation Component" tab for any proposed new substation, for example).
| 3.b. | Provide a component project cost breakdown into the identified categories along with a total component cost. Costs should be in current year dollars.
| 3.c. | If this proposal is being submitted as Market Efficiency project, provide an in-service year component project total cost.
| 3.d. | Identify the entity who will be designated the component.
4. | Transmission Line Reconductor/Rebuild Component Tab
Note: A tab should be created for each component based upon the type. Create additional tabs if needed.
| 4.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 4.b. | Identify the line terminal points. Add additional spaces if required.
Existing line physical characteristics
| 4.c. | Provide the size and type conductor that will be removed.
| 4.d. | Indicate whether the existing line hardware will be reused. If so, provide the age and condition of the hardware.
| 4.e. | Provide the condition and age of the existing structures. Describe the findings of any recent inspections or of analysis that has indicated a need for structural repair or reinforcement to re-conductor the line.
| 4.f. | Describe the terrain that the existing line traverses. Additionally, provide a Google Earth .KMZ file with the existing line path as an included docutment with the project proposal package.
Reconductor/rebuild component plan
| 4.g. | Provide the target ratings for the line.
| 4.h. | Provide the type and size of the conductor to be installed.
| 4.i. | If the shield wire is to be replaced, identify the type and size to be used.
| 4.j. | Describe the amount of the line that is anticipated to be rebuilt versus reconductored. Provide any assumptions that were used in arriving at this determination. If specific line sections have been identified for rebuild, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
| 4.k. | Describe the segments of the existing right-of-way that will need to be expanded or any newly required rights-of-way that will be required. If new or expanded right-of-way is required, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
| 4.l. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
5. | Substation Upgrade Component Tab
Note: A tab should be created for each component based upon the type. Create additional tabs if needed.
| 5.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 5.b. | Identify the name of the existing substation where the upgrade will take place.
| 5.c. | Describe the scope of the upgrade work at the identified substation.
| 5.d. | Describe any new substation equipment and provide the equipment ratings.
| 5.e. | Describe the assumptions that were made about the substation that were used in developing the scope and cost for the upgrade. For example, the use of a bay that appears to be available, the proposed use of an open area within the substation or the relocation of existing equipment.
| 5.f. | If the upgrade changes or expands upon the substation configuration provide a single line diagram and a station general arrangement drawing. These documents should be provided on the 'Redacted Information' tab under the appropriate project component.
| 5.g. | If the substation fence needs to be expanded, indicate the real-estate plan for acquiring the needed land. Also, provide a Google Earth .KMZ file detailing the expansion.
| 5.h. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
6. | Transmission Line Component Tab
Note: A tab should be created for each component based upon the type. Create additional tabs if needed.
| 6.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 6.b. | Provide the substation endpoints for the proposed transmission line component.
| 6.c. | Provide the target ratings for the proposed line.
| 6.d. | Provide the proposed conductor type and size.
| 6.e. | Provide a general description of the line, including nominal voltage, whether the facility will be AC or DC and if the construction will be overhead, underground, submarine or some combination.
| 6.f. | Provide a general description of the evaluated routes or routing study area. Provide a Google Earth .KMZ file with the evaluated routes or study plan.
| 6.g. | Describe the terrain traversed by the proposed new line.
| 6.h. | Route description by segment that includes lengths and widths and classified by whether the segment will be new right of way, an expansion of an existing right of way or use an existing right of way. This information may be included with the Google Earth .KMZ.
| 6.i. | Provide the project right of way and land acquisition plan and approach for both public and private lands.
| 6.j. | Provide the location and plan for any transmission facility crossings.
| 6.k. | Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
| 6.l. | Proposed tower characteristics such as monopole, lattice, wood h-frame design, double or single circuit, and horizontal, vertical or delta conductor configurations. Note, preliminary drawings for proposed structure types are acceptable in place of a written description.
| 6.m. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
7. | Greenfield Substation Component Tab
Note: A tab should be created for each component based upon the type. Create additional tabs if needed.
| 7.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 7.b. | Provide the name for the proposed substation.
| 7.c. | Provide the latitude and longitude (in decimal degrees) of the site(s) evaluated for the substation.
| 7.d. | Provide a general description of the substation. Also, provide a single line diagram and general arrangement drawing.
| 7.e. | Describe the major substation equipment and provide the equipment ratings.
| 7.f. | Describe the geography and current land use for the proposed site(s).
| 7.g. | Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
| 7.h. | Community and landowner outreach plan
| 7.i. | Provide the project land acquisition plan and approach for both public and private lands.
| 7.j. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
8. | Redacted information Tab
Provide all redacted information on this tab with a reference to the tab and specific question identification.
9. | Project Financial Information Tab
Project Schedule
| 9.a. | Provide the planned construction period, include the month and year of when capital spend will begin, when construction will begin and when construction will end. The final construction month should be the month preceding the commercial operation month.
Project Capital Expenditures
| 9.b. | Provide, in present year dollars, capital expenditure estimates by year for the Proposing Entity, work to be completed by others (e.g. incumbent TO) and total project. Capital expenditure estimates should include all capital expenditure, including any ongoing expenditures, for which the Proposing Entity plans to seek FERC approval for recovery.
| 9.c. | Even if AFUDC is not going to be employed, provide a yearly AFUDC cash flow.
| 9.d. | Provide any assumptions for the capital expenditure estimate (e.g. design assumptions, weather, manpower needed and work schedule, number of hours per day, construction area access, etc.).
| 9.e. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
10. | Cost Containment Commitment Tab
| 10.a. | Indicate if a binding capital cost commitment is being proposed.
| 10.b. | Indicate what project scope is covered by the proposed cost containment commitment. Identify the components covered by number.
| 10.b.i. | Provide, in present year dollars and year of occurrence dollars, the Proposing Entity's proposed binding cap on capital expenditures.
| 10.b.ii. | Provide any additional information related to the cap on capital expenditures, including but not limited to: if AFUDC is included in the cap, if all costs prior to commercial operation date are included in the cap, if the cap includes a variable or fixed inflation rate, etc.
| 10.b.iii. | Indicate which components of capital costs fall under the cost cap.
| 10.c. | Describe any other cost containment measures not detailed above.
| 10.d. | Provide the cost containment commitment legal language.
| 10.e. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 1. Executive Summary
Executive Summary
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
1. | Executive Summary
|  |  | Inputs |  | Instructions
|  | 1.a. | Proposing Entity name |  | Provide the name of the Proposing Entity. If there are multiple entities, please identify each party.
|  | 1.b. | Proposal window |  | Provide the RTEP Proposal Window in which this proposal is being submitted.
|  | 1.c. | Proposal identification |  | Provide the Proposing Entity project proposal id. Use "A, B, C, …", etc. to differentiate between proposals.
|  | 1.d. | General project description |  | Provide a General Description of the scope of this project, including the associated violation/issue being addressed and the type of regional/interregional analysis or process that identified the violation/issue.
|  | 1.e. | Tie line impact | Choose Yes or No | Identify if the proposal or a proposal component span between two PJM Transmission Owner zones. This group includes transmission that spans two or more affiliated companies (e.g. Meted and Allegheny Power).
|  | 1.f. | Interregional project | Choose Yes or No | Indicate if the project is being proposed as a solution to a Cross-Border issue. (Note: The Proposing Entity is responsible for initiating and satisfying all Regional and Interregional requirements.)
|  | 1.g. | Construct, own, operate and maintain | Choose Yes or No | Indicate if the Proposing Entity intends to construct, own, operate, and maintain the infrastructure built under this proposal.
|  | 1.h. | Whole or component project consideration |  | Provide a description of how the project should be considered; only as a whole or if portions of the project should be considered as well. (Separable portions/combinations should be submitted as separate proposals. If a proposal is submitted with multiple options, PJM will split it into multiple proposals. PJM reserves the right to select the best project, regardless of how it is packaged by Proposing Entities.)
|  | 1.i. | Project cost estimate (current year) |  | Total current year project cost estimate including estimates for any required Transmission Owner upgrades.
|  | 1.j. | Project cost estimate (in-service year) |  | Total in-service year project cost estimate including estimates for any required Transmission Owner upgrades.
|  | 1.k. | Project schedule duration |  | Project estimated schedule duration in months.
|  | 1.l. | Cost containment commitment | Choose Yes or No | Indicate if any cost containment commitment is being proposed as part of the project. If yes, the "Cost Containment" tab within this project proposal template is to be completed
|  | 1.m. | Additional benefits |  | If the project provides any additional benefits above solving the identified violations or constraints, identify those benefits.
If the answer to the Cross-Border question above at 1.f. was yes, complete the questions below.
|  | 1.n.i. | Interregional Cost Allocation Evaluation | Choose Yes or No | Indicate if an evaluation for Interregional Cost Allocation is desired.
|  | 1.n.ii. | Evaluated in interregional analysis under PJM Tariff or Operating Agreement provisions | Choose Yes or No | Indicate if the proposal has been evaluated in a coordinated interregional analysis under the PJM Tariff or Operating Agreement provisions. Specify the analysis and applicable Tariff or Operating Agreement provisions.
If 'yes,' specify analysis and applicable Tariff or Operating Agreement provisions
|  | 1.n.iii. | Regional and Interregional violations and issues from the Regional and/or Interregional analyses that identified the violations and issues addressed by the proposal. |  | List the specific Regional and Interregional violations and issues from the Regional and/or Interregional analyses that identified the violations and issues addressed by the proposal.

## 2. Overloaded Facilities
Overloaded Facilities
To be publically posted by PJM
2. | Overloaded Facilities
Facilities addressed by the proposed project
| 2.a. | FG # | Analysis Type | Bus # | Facility Name | To Bus # | To Bus Name | CKT | Voltage | Area
Facilities not addressed/caused by the proposed project
| 2.b. | FG # | Analysis Type | Bus # | Facility Name | To Bus # | To Bus Name | CKT | Voltage | Area

## 3. Project Components
Project Components
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
3. | Project Components
|  |  |  | Component 1 | Component 2 | Component 3 | Component 4 | Component 5 | Component 6 | Component 7 | Component 8 | Component 9 | Component 10
| 3.a. |  | Component description(s)
| 3.b. |  | Component cost (current year)
Engineering and design
Permitting / routing / siting
ROW / land acquisition
Materials and equipment
Construction and commissioning
Construction management
Overheads and miscellaneous costs
Contingency
Total component cost
| 3.c. |  | Component cost (in-service year)
| 3.d. |  | Construction responsibility

## 4. Reconduct-Rebuild Comp
Reconductor/Rebuild Transmission Line Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
4. | Transmission Line Reconductor/Rebuild Component
|  |  | Inputs | Instructions
|  | 4.a. | Component number | Provide the corresponding component number from the "Project Components" tab of the proposal template.
|  | 4.b. | Terminal points | Identify the line terminal points. Add additional spaces if required.
Existing Line Physical Characteristics
|  | 4.c. | Existing conductor size and type | Provide the size and type conductor that will be removed.
|  | 4.d. | Existing hardware plan
Indicate whether the existing line hardware will be reused. If so, provide the age and condition of the hardware.
|  | 4.e. | Existing tower line characteristics
Provide the condition and age of the existing structures. Describe the findings of any recent inspections or of analysis that has indicated a need for structural repair or reinforcement to re-conductor the line.
|  | 4.f. | Terrain description
Describe the terrain that the existing line traverses. Additionally, provide a Google Earth .KMZ file with the existing line path as an included docutment with the project proposal package.
Reconductor/Rebuild Component Plan
|  | 4.g. | Component target ratings | Provide the target ratings for the line.
|  | 4.h. | Proposed conductor size and type | Provide the type and size of the conductor to be installed.
|  | 4.i. | Proposed shield wire size and type | If the shield wire is to be replaced, identify the type and size to be used.
|  | 4.j. | Rebuild portion
Describe the amount of the line that is anticipated to be rebuilt versus reconductored. Provide any assumptions that were used in arriving at this determination. If specific line sections have been identified for rebuild, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
|  | 4.k. | Right of way
Describe the segments of the existing right-of-way that will need to be expanded or any newly required rights-of-way that will be required. If new or expanded right-of-way is required, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
|  | 4.l. | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 5. Sub Upgrade Comp
Substation Upgrade Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
5. | Substation Upgrade Component
|  |  | Inputs | Instructions
|  | 5.a. | Component number | Provide the corresponding component number from the "Project Components" tab of the proposal template.
|  | 5.b. | Substation | Identify the name of the existing substation where the upgrade will take place.
|  | 5.c. | Substation upgrade scope
Describe the scope of the upgrade work at the identified substation.
|  | 5.d. | New equipment description
Describe any new substation equipment and provide the equipment ratings.
|  | 5.e. | Substation assumptions
Describe the assumptions that were made about the substation that were used in developing the scope and cost for the upgrade. For example, the use of a bay that appears to be available, the proposed use of an open area within the substation or the relocation of existing equipment.
|  | 5.f. | Substation drawings | If the upgrade changes or expands upon the substation configuration provide a single line diagram and a station general arrangement drawing. These documents should be provided on the 'Redacted Information' tab under the appropriate project component.
|  | 5.g. | Real-estate plan
If the substation fence needs to be expanded, indicate the real-estate plan for acquiring the needed land. Also, provide a Google Earth .KMZ file detailing the expansion.
|  | 5.h. | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 6. Greenfield Line Comp
Greenfield Transmission Line Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
6. | Transmission Line Component
|  |  | Inputs | Instructions
|  | 6.a. | Component Number | Provide the corresponding component number from the "Project Components" tab of the proposal template.
|  | 6.b. | Line terminal points | Provide the substation endpoints for the proposed transmission line component.
|  | 6.c. | Project ratings | Provide the target ratings for the proposed line.
|  | 6.d. | Conductor type and size | Provide the proposed conductor type and size.
|  | 6.e. | General line description
Provide a general description of the line, including nominal voltage, whether the facility will be AC or DC and if the construction will be overhead, underground, submarine or some combination.
|  | 6.f. | General route description
Provide a general description of the evaluated routes or routing study area. Provide a Google Earth .KMZ file with the evaluated routes or study plan.
|  | 6.g. | Terrain description
Describe the terrain traversed by the proposed new line.
|  | 6.h. | Right of way plan by segment
Route description by segment that includes lengths and widths and classified by whether the segment will be new right of way, an expansion of an existing right of way or use an existing right of way. This information may be included with the Google Earth .KMZ.
|  | 6.i. | ROW and land acquisition plan
Provide the project right of way and land acquisition plan and approach for both public and private lands.
|  | 6.j. | Transmission facility crossings
Provide the location and plan for any transmission facility crossings.
|  | 6.k. | Environmental impacts
Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
|  | 6.l. | Tower characteristics
Proposed tower characteristics such as monopole, lattice, wood h-frame design, double or single circuit, and horizontal, vertical or delta conductor configurations. Note, preliminary drawings for proposed structure types are acceptable in place of a written description.
|  | 6.m. | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 7. Greenfield Sub Comp
Greenfield Substation Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
7. | Greenfield Substation Component
|  |  | Inputs | Instructions
|  | 7.a. | Component number | Provide the corresponding component number from the "Project Components" tab of the proposal template.
|  | 7.b. | Proposed substation name | Provide the name for the proposed substation.
|  | 7.c. | Evaluated location(s) | Provide the latitude and longitude (in decimal degrees) of the site(s) evaluated for the substation.
|  | 7.d. | Substation description
Provide a general description of the substation. Also, provide a single line diagram and general arrangement drawing.
|  | 7.e. | Substation description
Describe the major substation equipment and provide the equipment ratings.
|  | 7.f. | Geography and land use
Describe the geography and current land use for the proposed site(s).
|  | 7.g. | Environmental assessment
Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
|  | 7.h. | Outreach plan
Community and landowner outreach plan
|  | 7.i. | Land acquisition plan
Provide the project land acquisition plan and approach for both public and private lands.
|  | 7.j. | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 8. Redacted Information
Redacted Information
8. | Redacted information
Redacted financial information
| Question ID | Redacted response
Cost containment redacted information
| Question ID | Redacted response
Component 1 redacted information
| Question ID | Redacted response
Component 2 redacted information
| Question ID | Redacted response
Component 3 redacted information
| Question ID | Redacted response
Component 4 redacted information
| Question ID | Redacted response
Component 5 redacted information
| Question ID | Redacted response
Component 6 redacted information
| Question ID | Redacted response
Component 7 redacted information
| Question ID | Redacted response
Component 8 redacted information
| Question ID | Redacted response
Component 9 redacted information
| Question ID | Redacted response
Component 10 redacted information
| Question ID | Redacted response

## 9. Financial
Project Financial Information
Blue indicates input cells for the Proposing Entity to complete
9. | Project Financial Information
|  |  | Inputs |  |  |  |  | Instructions
Project Schedule
| 9.a. |  | Capital spend start date (Mo-Yr) | 2019-01-01 |  |  |  | Provide the planned construction period, include the month and year of when capital spend will begin, when construction will begin and when construction will end. The final construction month should be the month preceding the commercial operation month.
Construction start date (Mo-Yr)
|  |  | Commercial operation date (Mo-Yr) | 2023-01-01
Project Capital Expenditures
| 9.b. |  | Capital expenditure details | Total | 2019-01-01 | 2020-01-01 | 2021-01-02 | 2022-01-04 | 2023-01-06 | 2024-01-08 | Provide, in present year dollars, capital expenditure estimates by year for the Proposing Entity, work to be completed by others (e.g. incumbent TO) and total project. Capital expenditure estimates should include all capital expenditure, including any ongoing expenditures, for which the Proposing Entity plans to seek FERC approval for recovery.
Engineering and design
Permitting / routing / siting
ROW / land acquisition
Materials and equipment
Construction and commissioning
Construction management
Overheads and miscellaneous costs
Contingency
Proposer total capex
Work by others capex
Total project capex
| 9.c. |  |  | Total | 2019-01-01 | 2020-01-01 | 2021-01-02 | 2022-01-04 | 2023-01-06 | 2024-01-08 | Even if AFUDC is not going to be employed, provide a yearly AFUDC cash flow.
AFUDC
| 9.d. |  | Assumptions for the capital expenditure estimate
Provide any assumptions for the capital expenditure estimate (e.g. design assumptions, weather, manpower needed and work schedule, number of hours per day, construction area access, etc.).
| 9.e. |  | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.
[10 empty] | Yes | CWIP
[10 empty] | No | AFUDC
Not Yet Determined

## 10. Cost Contain
Cost Containment Commitment
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
10. | Cost Containment Commitment
|  |  | Inputs |  | Instructions
|  | 10.a. | Is the Proposer offering a binding cap on capital costs? | Choose Yes or No | Indicate if a binding capital cost commitment is being proposed.
|  | 10.b. | Project scope covered by the cost containment commitment
Indicate what project scope is covered by the proposed cost containment commitment. Identify the components covered by number.
[6 empty] | No | AFUDC
|  | 10.b.i. | Cost cap in present year dollars |  | Provide, in present year dollars and year of occurrence dollars, the Proposing Entity's proposed binding cap on capital expenditures. |  | Not Yet Determined
Cost cap in in-service year dollars
|  | 10.b.ii. | AdditionaliInformation on cost cap:
Provide any additional information related to the cap on capital expenditures, including but not limited to: if AFUDC is included in the cap, if all costs prior to commercial operation date are included in the cap, if the cap includes a variable or fixed inflation rate, etc.
|  | 10.b.iii. | Cost containment capital expenditure exemptions
|  |  | Capital cost component | Component covered by cost containment | Indicate which components of capital costs fall under the cost cap.
|  |  | Engineering and design | Choose Yes or No
|  |  | Permitting / routing / siting | Choose Yes or No
|  |  | ROW / land acquisition | Choose Yes or No
|  |  | Materials and equipment | Choose Yes or No
|  |  | Construction and commissioning | Choose Yes or No
|  |  | Construction management | Choose Yes or No
|  |  | Overheads and miscellaneous costs | Choose Yes or No
|  |  | Taxes | Choose Yes or No
|  |  | AFUDC | Choose Yes or No
|  |  | Escalation | Choose Yes or No
|  | 10.c. | Describe any other Cost Containment Measures not covered above:
Describe any other cost containment measures not detailed above.
|  | 10.d. | Cost Commitment Legal Language
Provide the cost containment commitment legal language.
|  | 10.e. | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.
Yes
No