## Meeting Content (hidden)
Capacity Senior Task Force Meeting Content
Meeting
| 1 | 2 | 3 | 4 | 5 | 6
| 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon
Topic(s) | 2012-04-12 | 2012-04-19 | 2012-04-27 | 2012-05-04 | 2012-05-22 | 2012-06-06 | 2012-06-28 | 2012-07-26 | 2012-08-01
Admin | bar: 2012-04-12
Charter | bar: 2012-04-12 to 2012-04-19
Work Plan | bar: 2012-04-12
Provide Education | bar: 2012-04-12
Document Interests | bar: 2012-04-19
Develop Design Components | bar: 2012-04-19 to 2012-04-27
Develop Solution Options | bar: 2012-04-27 to 2012-05-04
Reduce Solution Options | bar: 2012-05-04
Package Solutions | bar: 2012-05-04 to 2012-05-22
Reduce Package Options | bar: 2012-05-22 to 2012-06-06
Build Concensus | bar: 2012-06-06
Vote at MRC/MC | 2012-06-28: First Read; 2012-07-26: X
File with FERC | bar: 2012-08-01

## With dates (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProvide Education
Proposal Development |  |  | 13 |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
Problem Investigation |  |  |  | 20
Proposal Development |  |  |  |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
Demand Response Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | Mar. 2013
üProvide Education
Document Interests |  |  |  | 20
Develop & Refine Design Components | [5 empty] | 14
Develop & Refine Solution Options | [6 empty] | 5
Develop & Refine Solution Packages
Build Consensus
First Read @ MRC
Vote at MRC/MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
Refine Interests |  |  | 13
Refine Design Components
Develop & Refine Solution Options |  |  |  |  | 2012-10-01: 11; 2012-11-01: 14
Develop & Refine Solution Packages |  |  |  |  | 2012-12-01: 5
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC/MC | bar: 2013-04-01
FERC Filing |  |  |  |  | 2013-05-01: 2012-05-31

## 2012- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
Proposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
üRefine Interests
üRefine Design Components
Develop & Refine Component Options | bar: 2012-10-01 to 2012-11-01
Develop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC | bar: 2013-04-01
Vote at MC | bar: 2013-05-01
FERC Filing |  |  |  | 2013-05-01: 2012-05-31

## 2013- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
|  |  | 2012 |  |  |  | 2013
2012 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
üProvide Education
Document Interests | bar: Oct
Develop & Refine Design Components | bar: Nov
Develop & Refine Component Options | bar: Dec to 2013 Jan
Develop & Refine Solution Packages | bar: 2013 Feb to 2013 Mar
Build Consensus | bar: 2013 Mar to 2013 Apr
First Read @ MRC | bar: 2013 Apr
Vote at MRC | bar: 2013 May
Vote at MC | bar: 2013 Jun
|  |  | 2012 | 2013 Jan: 2013
2013 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Provide Education | bar: 2013 Jan
Document Interests | bar: 2013 Feb
Develop & Refine Design Components | bar: 2013 Feb to 2013 Mar
Develop & Refine Component Options | bar: 2013 Apr to 2013 May
Develop & Refine Solution Packages | bar: 2013 Jun
Build Consensus | bar: 2013 Jul to 2013 Aug
First Read @ MRC | bar: 2013 Sep
Vote at MRC | bar: 2013 Oct
Vote at MC | bar: 2013 Nov

## 2014 - Detailed Schedule
Gas Unit Commitment Coordination (OC) - 2014 Work Plan
Last updated: 7/18/14
Gas Unit Commitment Coordination (OC) | Mtg 1 | Mtg 2 | Mtg 3 | Mtg 4 | Mtg 5 | Mtg 6 | Mtg 7 | Mtg 8 | Mtg 9 | Mtg 10 | Mtg 11 | Mtg 12 | Mtg 13
| 6/23/2014 OC | 7/8/2014 OC | 7/23/2014 12-3pm | 8/5/2014 OC | 8/20/2014 1-4pm | 9/4/2014 OC | 9/16/2014 9-12pm | 10/7/2014 OC | 10/20/2014 9-12pm | 11/6/14 OC | 11/18/2014 9-12pm | 12/2/2014 OC | 12/22/2014 9-12pm
Kick Off | bar: Mtg 1
Review Problem Statement and Issue Charge | bar: Mtg 2
Develop and Review Work Plan | bar: Mtg 2
Document Interests & Priorities | bar: Mtg 2
Provide Education | bar: Mtg 2 to Mtg 13
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages
Build Consensus
Polling

## 1. Interest Identification
Gas Unit Commitment Coordination (OC)
Interest Identification
1 | Clear communication between operators with understood obligations on both sides. Units that operator over multiple days and outside of the market- continued communications
2 | Continued communications between operators for units that operate over multiple days and are outside of the market
3 | Confirmation if communication is a directive
4 | How will fuel costs be settled if a generator is cancelled
5 | Consideration of impact on the units themselves when running with dual fuel capability that can be switched on the fly- operations and maintenance considered in the solution
6 | Dispatcher actions reflected in LMP to minimize up-lift (ERPIV)
7 | Long lead unit commitment procedures for units with greater than 24 hour startup and notification times and how it is handled in the DA Market
8 | Impact of external units that are pseudo tied and dynamically scheduled
9 | Clarity in process and impacts of switching schedules in operating day
10 | Finding appropriate way method for generation owners to communicate changing notification start times due to restrictions (currently via phone) and when outside market windows
11 | Clarification on topics being discussed in other groups
12 | Prices and dispatch instructions (to come on/off line) Prices and compensation should be consistent with dispatch instructions (to come on/off line). Binding commitment is consistent with PJM instructions
13 | Generation Owners to report costs and unit limit changes associated with operations on super cold days (i.e.- unit can operate on oil, but due to cold needs to be started with gas)
14 | While providing flexibility for fuel-limited units, do not create disparities for units that don’t have the same fuel issues.
15 | Consider limiting some of these coordination activities to times of stress or extreme events.
16 | Limiting some required coordination to times of extreme events
17 | Clarifying what it means to be available in Real Time (clarify tariff language and other items- manuals, etc.).
18 | Clear communication between operators and generators that is consistent with tariff limitations
19 | PJM operators are trained on limits of authority and are clear in instructions. No ambiguous directives. Dispatch can not issue directives beyond their ability and authority and can not over-rule the tariff
20 | Operational constraints that are being given to PJM dispatch are consistent with gas nomination timelines. Gas units - type of transportation information provided to dispatch, backup fuel (arrangements). Operational limitations so units are not over committed
21 | Cost of providing services due to rule changes needs to be kept in mind
22 | Shouldn’t limit approaches to fuel acquisition- keep flexibility. Dispatchers need to be aware of fuel and transportation availability and back up fuel arrangements (this will allow for better operational awareness)
23 | Improve generator performance
24 | Consistent with capacity market rules
25 | Sharing of operational limitation data
26 | Ensuring dispatch scheduling process results in the least cost objective is met (minimize overall costs). PJM should have a full understanding of what we are buying
27 | Fuel procurement risk is not transferred to consumers
28 | Consider tool enhancements for operators to manage processes (integrate tools)

## Issue Topics
Gas Unit Commitment Coordination (OC)
Issue Topics
# | TOPIC | Priority | Education Materials/ Topics
1 | “Firmness” Binding PJM operator unit commitment decisions outside of Day-Ahead market (focus on communications). | High | 1- Transcription tapes 2- Approach to scheduling for the day 3- Section 4.2.4 of PJM Manual 01 distinguishes dispatch or operating instructions from directives overview 4- How physically and financially binding are these dispatch communications?
2a | Obligations of PJM capacity units with respect to fuel availability |  | 1-Education from CSTF and/or RPM 2- Discuss definition of obligation (to bid into DA Market and to make unit available)
2b | How the following are defined and considered: o Economic vs. reliability outages o Outages that impact Equivalent Forced Outage Rate Peak (EFORp) o Outages considered out of management control
3a | PJM unit commitment practices for units requiring significant advance notice for fuel procurement.
3b | Long lead unit commitment procedures for units with greater than 24 hour startup and notification times.
3c | Methods to ensure long lead generation commitments are accurately reflected in Day- Ahead market. |  | 1- Discuss how manually committed units are handled in the DA 2- Close coordination with Unit Market Offer problem statement
3d | Flexibility of generator startup time and notification time data fields in unit offer data. Can the existing data fields accurately model the situations seen in January? Do the existing market rules support this? |  | 1- Review current data that is provided by generators and discuss additional data that can be provided 2- Review what the flexibility is with generator start up notification time today and is what is in place sufficient?
4a | Ability to track dual fuel capability and availability in real-time, including requirements and rules for a generator to switch schedules
4b | Requirements and tools for managing limited fuel availability (to include units whose primary fuel may not be natural gas but that require gas to start) and unit flexibility parameters (e.g. units that may be able to get some gas to run during peak hours only) PJM “Cancellation Costs” recovery for generators cancelled prior to expected run times in real time |  | 1- Review all fuel types and requirements 2- Review different types of scenarios for cancellation costs when a generator is following PJM Dispatch instruction.

## Commun. Issues Design Component
Gas Unit Commitment Coordination (OC): Communication Issues
OPTIONS MATRIX
Solution Options2
# | Design Components1 | Priority | Status Quo | A | B | C | D | E
1
2
3
4
5 | [8 empty] | Low
6 | [8 empty] | Low - Medium
7 | [8 empty] | Low - High
8 | [8 empty] | Medium
9 | [8 empty] | Medium - High
10 | [8 empty] | High
11
12
Instructions:
1Design Components - each is an "attibute" or "component" of any proposed solution. Consensus of the group should be sought on selection of a set of solution criteria.
2Solution Options - each is a solution alternative elicited from the stakeholder group that meet one of the specific solution criteria.
To complete the matrix:
1. Elicit from the stakeholder group a set of components (attributes) desired for any proposed solution. Enter a short label for each in the Design Components column.
2. If needed, enter a more detailed description of each criteria on the "Component Details" tab.
3. Using informal/non-binding voting, rate each component's priority in the final solution as "high/medium/low"
4. Elicit from the stakeholder group potential solution alternative(s) for each component. Enter a short label for each in the Solution Options columns.
5. If needed, enter a more detailed description of each potential solution option on the "Solution Details" tab.
6. Once the matrix is filled out, the group will attempt to select a single solution alternative (column) for each component (row) to form a solution "package".
Example: cells 1B, 2C, 3A, 4B, 5D could make up a solution package.
7. If consensus is achieved on a single package (Tier 1 decision-making method), this will be documented in a Consensus Proposal Report to the parent committee.
8. If not, the group will identify up to 3 possible solution packages in a comparative Proposal Alternatives Report to the parent committee (Tier 2 decsion-making method).

## 2a. Component Details
Gas Unit Commitment Coordination (OC)
COMPONENT DETAILS
Instructions: Complete this form as needed. Design components should be populated from the Options Matrix.
Design Component |  | Detailed Description
1 |  | <enter detailed description of this component>
2 |  | <enter detailed description of this component>
3 |  | <enter detailed description of this component>
4 |  | <enter detailed description of this component>
5 |  | <enter detailed description of this component>

## 2b. Solution Details
Gas Unit Commitment Coordination (OC)
SOLUTION DETAILS
Instructions: Complete this form as needed. Potential solutions should be populated from the Proposal Matrix
Package Solutions2
| A | B | C | D | E
1
2
3
4
5

## 3. Package Matrix
Gas Unit Commitment Coordination (OC)
PACKAGE/ PROPOSAL MATRIX
Instructions:
1. Copy over design component, priority, and status quo columns from options matrix
2. Complete individual packages in columns by selecting individual component options from the options matrix.
Packages
# | Design Components | Priority | Status Quo | A | B | C | D | E
1
2
3
4
5
6
7
8
9 | [8 empty] | Low
10 | [8 empty] | Low - Medium
Low - High
Medium
Medium - High
High

## Parking Lot
Gas Unit Commitment Coordination (OC)
Parking Lot
Instructions: Use this space to document any items not specific to another topic area.
Description