## Notes
Please see example tempate for details on how to fill out this template:
http://pjm.com/~/media/planning/rtep-dev/expan-plan-process/ferc-order-1000/rtep-proposal-windows/2014-rtep-proposal-window-template.ashx
Notes for Proposal Template
1. Costs for each componenet as well as total cost must be provided (in current year dollars for all proposals. Additionally cost in In-Service Year dollars must be provided for Market Efficiency Proposals)
2. Any nearby overloads not addressed, or violations casued by proposal not addressed must be included
PJM requires the following Files to be provided
1. Idevs to model the proposed upgrade for each component (please only use unused bus numbers for the creation of new buses)
2. Updated Contingency if upgrade is a new facility or changes the configuration of an existing facility
3. Single line diagram if upgrade is new facility or changes the configuration of an existing facility
4. Project specifics, including by not limited to: Conductor type, mileage, tower type, configuration and technology
For more detailed projects an additional narrative may be needed to addreses specifics of a project including (when applicible):
1. Short Circuit and Stability evidence
2. Location plan for work at existing substations
3. Ariel map of the project that reflects route(s) for new facilities
4. Assumtions and/or modifications associated with any protection and control (relaying) work at existing stations
5. Durations and Outages of existing facilities required to complete construction
6. Right of ways, siting and permiting

## Proposal Template
2015 RTEP Proposal Template - EXAMPLE
Proposing Entity: XYZ Transmission Developer
Proposal Window: 2015_1
Proposal ID #: A
Overloaded Facilities | [6 empty] | Proposal Information (public posting) | [5 empty] | Detailed Proposal Information
FG # | Analysis Type | Bus # | Facility Name | To Bus # | To Bus Name | CKT | Upgrade/Greenfield | Proposing Entity | Total Project Cost | Target Zone(s) | kV Level | General Description/Scope | Component 1 | Component 2 | Component 3 | Component 4 | Component 5 | Component 6 | Component 7 | Component 8 | Component 9 | Component 10
LL-28 | Light Load | 272367 | ROCK FALL; R | 272095 | NELSON ; R | 1 | Greenfield | XYZ Transmission Developer | $107.4M | ComEd | 138 | Tie together Bus A – Bus B 500 kV line and the Bus C – Bus D 500 kV line at a new station location that is adjacent to the existing line cooridor. The new station to tie these lines together will be built with six 500 kV breakers and four line exits: one to Bus A, one to Bus B, and two to BUS E. | Detailed Component 1 | Detailed component 2 | Detailed Component 3
N2-VD49 | N-1-1 Voltage Drop | 314756 | 3DOUBLDY | [6 empty] | Dominion | 115
N2-VM2 | N-1-1 Voltage Magnitude | 204615 | 27GLENDON | [6 empty] | Meted | 138
2.1 | N-1-1 Thermal | 314815 | 3OAK GRE | 314769 | 3ORANGE | 1 |  |  |  | Dominion | 115
Nearby Overloads not addressed by propal/caused by proposal | [11 empty] | Cost of each Componenet | 50.1 | 7.3 | 50 | $ | $ | $ | $ | $ | $ | $
1.7 | N-1-1 Thermal | 314768 | 3MITCHEL | 314345 | 3MT RUN | 1 | [5 empty] | Anticipated IS Date: 6/1/2020
N/A | N-1 Thermal | 314815 | 3OAK GRE | 314769 | 3ORANGE | 1 | [5 empty] | Expected Outages Need for construction: 3 Month Outage of Line A - Line B and Line C - Line D needed in the fall of 2018
Additional Benefits: This proposal will alleviate the need for Supplemental Project SXXXX and additionaly reduces congestion on the 1234/5678 Interface
This project or a portion of this project spans (e.g. ties between or taps) between two PJM Transmission Owner zones or between PJM and a neighboring Balancing Authority. This group includes transmission that spans two or more affiliated companies (e.g. MetEd and Allegheny Power).
Note on A5: Michael Herman1: Please use A,B,C,D etc to differentiate your proposals