## 2023 WORK PLAN
Distributed Resources Subcommittee (DISRS) - Work Plan
Updated: July 26, 2023 |  | 2023
Working Items | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
DER Aggregation / Order 2222 - Active
Triennial Review Timing
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC
üVote at MRC
üVote at MC
Multi-Year Pricing Mechanism
üProvide Education
üRefine Interests
üDevelop & Refine Design Components
üDevelop & Refine Component Options
üDevelop & Refine Solution Packages
üBuild Consensus
üFirst Read @ MRC
Vote at MRC
Vote at MC
FERC Filing
Capacity Compliance Weather Sensitive Load - On Hold
Add Additional Energy Offer Parameters to Economic DR - Active
Detailed Work Plan -- Order 2222 Compliance | Previous DIRS Meetings | 1.9.2023 | 2.6.2023 | 3.6.2023 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 9.8.2023
Overview of the Order | X
Education | X
Stakeholder Feedback and Discussion | X
EDC Coordination Workshop - 2 hour meetings | X
Straw Proposal Discussion | X
Compliance Proposal Development | X
Compliance Filing - Tariff Review | X
Compliance Filing Due Date - Feb 1, 2022 | X | Awaiting FERC Order
Order on Compliance Filing - issued Mar 1, 2023, due Sept 1, 2023 (extension requested, pending) |  |  |  | X | X | X | X | X | X | X | X | X | X
Implementation Discussions
Order 2222 - Compliance Order - topics by meeting date
Capacity mitigation |  |  |  |  | X
Utility review process; information and data; dispatch agent; electric distribution company definition; operational coordination; | [5 empty] | X
Net Energy Metering; double counting; Metering and Telemetry; + previous topics | [6 empty] | X
Locational requirements; + previous topics | [7 empty] | X
Information and Data; reliability criteria; dispute resolution; + previous topics | [8 empty] | X
Continuous model and participaton criteria; +previous topics | [9 empty] | X
DER Opt-In, DR Opt-Out and Locational Requirements + previous topics | [10 empty] | X
Effective dates and Tariff redline review | [11 empty] | X
Compliance filing due to FERC by Sept 1, 2023 | [12 empty] | X
Detailed Work Plan -- Capacity Compliance Weather Sensitive Load | Previous DRS Meetings | 1.9.2023 | 2.6.2023 | 3.6.2022 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 9.8.2023
Provide Education
Review Documented Interests | X
Review Developed Design Components | X
Develop & Refine Component Options | X
Develop & Refine Solution Packages |  | X | X
Build Consensus |  |  |  | X
Report Recommended Solutions to MIC (& OC) |  |  |  |  | On Hold
Endorsement at MIC/OC
First Read - MRC
Endorsement - MRC
Detailed Work Plan -- Add additional energy offer parameters to econimic Demand Response | Previous DIRS or DRS Meetings | 1.9.2023 | 2.6.2023 | 3.6.2023 | 4.10.2023 | 5.8.2023 | 5.25.2023 | 6.5.2023 | 6.23.2023 | 7.14.2023 | 7.31.2023 | 8.16.2023 | 9.8.2023
Review Initial Issue Charge and Problem Statement | [5 empty] | X
Provide Status Update | [7 empty] | X
Review Updated Issue Charge | [9 empty] | X
Provide Education | [10 empty] | On Hold
Review Documented Interests
Review Developed Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages
Build Consensus
Report Recommended Solutions to MIC
Endorsement at MIC
First Read - MRC
Endorsement - MRC
Endorsement - MC