## Sheet1
Clean Attribute Procurement Senior Task Force (CAPSTF) - Work Plan | 6/3/22 | 6/28/22 | 7/22/22 | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Develop Work Plan | X | X
Education & Joint Fact-Finding | X | X | X | bar: Aug to Dec
Interest Identification |  | X | X
Develop Representative Market Design Options | X | X | X | bar: Aug to Sep
Develop Design Components |  |  | X | bar: Aug to Oct
Document Relative Importance of each Component | bar: Oct
Develop Options for each Component | bar: Sep to Feb
Narrow Options | bar: Dec to Feb
Develop Packages | bar: Jan to Apr
Narrow Packages | bar: Feb to May
Consensus Testing | bar: Apr to May
Tier 1/Tier 2 Decision Making | bar: Jun
Reporting to Parent Committee (MRC) | bar: Jun
Updated: May 31, 2022