## Meeting Content (hidden)
Capacity Senior Task Force Meeting Content
Meeting
| 1 | 2 | 3 | 4 | 5 | 6
| 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon
Topic(s) | 2012-04-12 | 2012-04-19 | 2012-04-27 | 2012-05-04 | 2012-05-22 | 2012-06-06 | 2012-06-28 | 2012-07-26 | 2012-08-01
Admin | bar: 2012-04-12
Charter | bar: 2012-04-12 to 2012-04-19
Work Plan | bar: 2012-04-12
Provide Education | bar: 2012-04-12
Document Interests | bar: 2012-04-19
Develop Design Components | bar: 2012-04-19 to 2012-04-27
Develop Solution Options | bar: 2012-04-27 to 2012-05-04
Reduce Solution Options | bar: 2012-05-04
Package Solutions | bar: 2012-05-04 to 2012-05-22
Reduce Package Options | bar: 2012-05-22 to 2012-06-06
Build Concensus | bar: 2012-06-06
Vote at MRC/MC | 2012-06-28: First Read; 2012-07-26: X
File with FERC | bar: 2012-08-01

## With dates (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProvide Education
Proposal Development |  |  | 13 |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
Problem Investigation |  |  |  | 20
Proposal Development |  |  |  |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
Demand Response Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | Mar. 2013
üProvide Education
Document Interests |  |  |  | 20
Develop & Refine Design Components | [5 empty] | 14
Develop & Refine Solution Options | [6 empty] | 5
Develop & Refine Solution Packages
Build Consensus
First Read @ MRC
Vote at MRC/MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
Refine Interests |  |  | 13
Refine Design Components
Develop & Refine Solution Options |  |  |  |  | 2012-10-01: 11; 2012-11-01: 14
Develop & Refine Solution Packages |  |  |  |  | 2012-12-01: 5
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC/MC | bar: 2013-04-01
FERC Filing |  |  |  |  | 2013-05-01: 2012-05-31

## 2012- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
Proposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
üRefine Interests
üRefine Design Components
Develop & Refine Component Options | bar: 2012-10-01 to 2012-11-01
Develop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC | bar: 2013-04-01
Vote at MC | bar: 2013-05-01
FERC Filing |  |  |  | 2013-05-01: 2012-05-31

## 2013- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
|  |  | 2012 |  |  |  | 2013
2012 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
üProvide Education
Document Interests | bar: Oct
Develop & Refine Design Components | bar: Nov
Develop & Refine Component Options | bar: Dec to 2013 Jan
Develop & Refine Solution Packages | bar: 2013 Feb to 2013 Mar
Build Consensus | bar: 2013 Mar to 2013 Apr
First Read @ MRC | bar: 2013 Apr
Vote at MRC | bar: 2013 May
Vote at MC | bar: 2013 Jun
|  |  | 2012 | 2013 Jan: 2013
2013 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Provide Education | bar: 2013 Jan
Document Interests | bar: 2013 Feb
Develop & Refine Design Components | bar: 2013 Feb to 2013 Mar
Develop & Refine Component Options | bar: 2013 Apr to 2013 May
Develop & Refine Solution Packages | bar: 2013 Jun
Build Consensus | bar: 2013 Jul to 2013 Aug
First Read @ MRC | bar: 2013 Sep
Vote at MRC | bar: 2013 Oct
Vote at MC | bar: 2013 Nov

## Workplan (Original)
2018 Summer-Only Senior Task Force (SODRSTF) Work Plan
Updated: January 6, 2017
Completed Items
Provide Education
Refine Interests
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
FERC Filing
Issue | December (2017) | February |  | March | April | May | June | July | August | September | October | November | December |  | January (2019) | February (2019) | March (2019)
Summer-Only DR Work Plan |  |  |  | November: SODRSTF Voting | MRC 1st Read | MRC Voting | MC Voting | PJM FERC Filing
SODRSTF Stakeholder Process
Updated: December 19, 2017
Detailed Work Plan | 2017-12-13 | 2018-02-02 | 2018-02-14 | 2018-03-09 | 2018-04-13 | 2018-05-09 | 2018-06-13 | 2018-07-09 | 2018-08-15 | 2018-09-19 | 2018-10-17 | 2018-11-19 | 2018-12-05 | 2018-12-06 | add dates | add dates | add dates
Create Charter | bar: 2017-12-13
Provide Education | bar: 2017-12-13 to 2018-05-09
Develop Work Plan | bar: 2018-02-02 to 2018-02-14
Document Interests | bar: 2018-02-02 to 2018-02-14
Develop & Refine Design Components | bar: 2018-02-14 to 2018-04-13
Develop & Refine Component Options | bar: 2018-03-09 to 2018-04-13
Develop & Refine Solution Packages | bar: 2018-05-09 to 2018-07-09
Build Consensus | bar: 2018-08-15 to 2018-10-17
SODRSTF Vote | bar: 2018-11-19
First Read @ MRC | bar: 2018-12-06
Vote at MRC | [14 empty] | x
Vote at MC | [15 empty] | x
FERC Filing | [16 empty] | x

## Workplan (Updated)
2018 Summer-Only Senior Task Force (SODRSTF) Work Plan
Updated: January 6, 2017
Completed Items
Provide Education
Refine Interests
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
FERC Filing
Issue | December (2017) | February |  | March | April | May | June |  | July |  | August |  | September
Summer-Only DR Work Plan | [10 empty] | SODRSTF Voting | MRC 1st Read | MRC Voting | MC Voting
SODRSTF Stakeholder Process
Updated: June 13, 2018
Detailed Work Plan | 2017-12-13 | 2018-02-02 | 2018-02-14 | 2018-03-09 | 2018-04-13 | 2018-05-09 | 2018-06-13 | 2018-06-29 | 2018-07-09 | 2018-07-25 | 2018-08-15 | 2018-08-23 | 2018-09-27 | 2018-09-27
Create Charter | x
Provide Education | x | x | x | x | x | x
Develop Work Plan |  | x | x
Document Interests |  | x | x
Develop & Refine Design Components |  |  | x | x | x
Develop & Refine Component Options |  |  |  | x | x
Develop & Refine Solution Packages | [5 empty] | x | x
Build Consensus | [6 empty] | x | x | x | x
SODRSTF Vote | [10 empty] | x
First Read @ MRC | [11 empty] | x
Vote at MRC | [12 empty] | x
Vote at MC | [13 empty] | x
FERC Filing
Additional Meeting Dates