## 2015 CWIP Worksheet filing
Public Service Electric and Gas Company
Annual Report of Construction Work In Progress (CWIP) in Transmission Rate Base
Federal Energy Regulatory Commission Authorized Incentive Projects
(per section 2B of PSE&G's Attachment H-10B Formula Rate Implementation Protocols)
PJM Project # | RTEP Project | Actual Projects Cost thru Dec 2015 | AFUDC Year 2009 | AFUDC Year 2010 | AFUDC Year 2011 | AFUDC Year 2012 | AFUDC Year 2013 | AFUDC Year 2014 | AFUDC Year 2015 | 2015 CWIP Revenue Requirement | Status | Projected In-Service Date
B0489 | Build new 500 kV transmission facilities from Pennsylvania - New Jersey border at Bushkill to Roseland (500 kV and above elements of the project) | 0 | 78361 | [6 empty] | 1955562.6148 | Completed | May 2015
B1398-B1398.7 | Mickleton - Gloucester-Camden | 0 | [7 empty] | 9560845.6658 | Completed | June 2015
B1398.15-B1398.19 | Mickleton - Gloucester-Camden | 0 | [7 empty] | 24003.1921 | Completed | June 2015
B1304.1-B1304.4 | Northeast Grid Reliability Project | 232789180.7997 |  |  | 32527.35 |  |  |  |  | 31772294.1741 | Under Construction | July 2016
B1304.5-B1304.21 | Northeast Grid Reliability Project | 31157349.1679 | [7 empty] | 2336444.6794 | Under Construction | July 2016
B2436.10-B2436.91 & B2437.10- B2437.33 | Bergen Linden Corridor | 225513179.81 | [5 empty] | 13595.93 |  | 12971220.1914 | Under Construction | May 2016-June 2018
| Total | 489459709.7776 | 78361 | 0 | 32527.35 | 0 | 0 | 13595.93 | 0 | 58620370.5176